## Read Me
TrustHome PH — Use Cases & Test Cases Catalog (rev. 2026-10-04)
Factual baseline: TrustHome_Current_Progress_Report_2026-10-04.md (PR #42 fixes working copy). Document references now point to the new TH-01…TH-09 PDF set; the old reference is kept in brackets in the Use Cases Source column.
Sheets
Use Cases — UC-01…UC-47 with actor, flows, postconditions, source, version and a new "Evidence (2026-10-04)" column.
Test Cases — all test cases; yellow columns (Status, Actual Result, Tester, Date) are for execution.
Summary — live COUNTIFS by module/status/origin; ranges now cover every row (previously stopped at row 167).
Requirements — revised and new FRs (was "Proposed FRs"): FR-005 revise, FR-020 revised, FR-025…FR-028 added.
Known Gaps — GAP-01…GAP-11 release risks with owner and exit criteria; BUG-008 marked resolved.
Status values
Passed = on deployed build · Passed (Dev) = dev/emulator/unit only · Failed = executed and failed · Blocked = environment dependency · Not Run = ready (Remarks say if a known gap makes failure expected) · Retired = feature removed.
Evidence labels (use separately, never interchangeably)
Implemented in source · Unit/emulator tested · Reported working by a user · Deployed/live verified · Known gap · Roadmap.
What changed in this revision
1. BUG-008 resolved: rules deployed 2026-10-04 → every previously Blocked case is now Not Run (re-run on emulator then live). TC-SEC-007 Passed.
2. Automated counts: Node tests 48 (TC-AUTO-001), Python tests 28 (TC-AUTO-004), emulator rules suite 9 (new TC-AUTO-006).
3. Cloudinary PDF delivery blocked (show_original_customer_untrusted): TC-VER-004 Failed; new TC-VER-008 (file privacy) and TC-VER-009 (Download link) Failed → GAP-01.
4. Booking approval now a client transaction: UC-15 rewritten; new TC-BOOK-019 (concurrency, GAP-02), 021–022 (emulator Passed (Dev)), 023 (user-reported approval).
5. Exact-address handoff not active: UC-20 / TC-MAP-009 flagged GAP-03.
6. Admin notifications cover listing submissions AND disputes: UC-29, TC-NOTIF-005/009 updated, TC-NOTIF-012 added, FR-020 revised.
7. Listing purpose rent/sale: sale not bookable (TC-BOOK-020, FR-025), purpose filter, fairness exclusions.
8. Bank catalog: Metrobank only, fail-closed validation, admin-queued jobs + worker (UC-33 rewritten, UC-47, TC-BANK-008…014).
9. Operations: backup/restore/migration use cases (UC-43…45) and TC-OPS-001…006 in new module "Operations & Data".
10. Jobs: completion and trust recompute run weekly via GitHub Actions; Firebase scheduled functions are not deployed (UC-19, TC-JOB-001).
How to use
Edit only the yellow columns in Test Cases. Example: Status = Passed · Actual Result = 'Booking created as Pending; owner bell shows 1' · Tester = Laurente · Date = 2026-10-05.
Run TC-DEP-001 (deploy current build) and TC-E2E-001 first; then promote "Passed (Dev)" rows by re-running them on the deployed build.

## Use Cases
UC ID | Use Case | Module | Primary Actor | Related FR | Preconditions | Main Flow | Alternate / Exception Flows | Postconditions | Source | Version | Evidence (2026-10-04)
UC-01 | Register an account | Authentication | Guest | FR-001 | Visitor is signed out. | 1. Open Login / Register. 2. Enter name, email, password. 3. Submit. 4. System creates Firebase Auth account and users/{uid} profile (role user, status active). 5. Redirect to home/dashboard. | A1. Email already in use -> inline error. A2. Weak/short password -> inline error. A3. Network failure -> error message, no partial profile. | User is signed in with an active user profile. | TH-03 §2; TH-04 §2, §4 (was: Build Instructions §2.3, §6; Firebase Setup §4) | v0.1 | Implemented in source
UC-02 | Log in with email and password | Authentication | User / Admin | FR-001 | Account exists. | 1. Open Login. 2. Enter email + password. 3. System authenticates and loads profile. 4. Redirect to the user's landing page. | A1. Wrong password / unknown email -> inline error, no session. A2. Suspended account -> suspended-account screen; protected actions blocked. | Session active; nav shows account menu + bell. | TH-03 §2; TH-04 §2, §4 (was: Build Instructions §6) | v0.1 | Implemented in source
UC-03 | Sign in with Google | Authentication | Guest / User | FR-001 | Google sign-in enabled in Firebase. | 1. Click Continue with Google. 2. Choose account. 3. On first sign-in, system creates users profile. 4. Redirect. | A1. User closes popup -> stays on login, no error loop. A2. Existing email/password account with same email -> handled without duplicate profile. | Signed in; single profile per UID. | TH-03 §2; TH-04 §2, §4 (was: Firebase Setup §4) | v0.1 | Implemented in source
UC-04 | Log out | Authentication | User / Admin | FR-001 | User is signed in. | 1. Open account menu. 2. Click Log out. 3. Session cleared; redirected to public page. | A1. Using back button after logout does not reveal protected pages. | Signed out. | TH-03 §2; TH-04 §2, §4 (was: Design Guide p.10) | v0.1 | Implemented in source
UC-05 | Manage profile / account | Account | User | FR-001 | Signed in. | 1. Open profile/account page. 2. Edit allowed fields (e.g., name). 3. Save. | A1. User cannot change own role or status (rules deny). | Profile updated; role/status unchanged. | TH-03 §2 (was: Progress Report v0.1) | v0.1 | Implemented in source
UC-06 | Create a listing and submit for review | Listing Intake | User (Owner) | FR-002, FR-003 | Signed in, active account. | 1. Open Create Listing (multi-step). 2. Enter title, property type, purpose (rent/sale), rental term, exact private address, city, price, rooms/bathrooms, floor/lot area, availability date, amenities, description. 3. Upload >= 4 photos to Cloudinary (image/auto). 4. Upload one ownership document + one government photo ID (PDF as raw resource). 5. Add >= 1 showing window (day + start/end time). 6. Optionally place an approximate map pin. 7. Submit -> one Firestore batch writes listings/{id} (verificationStatus pending, public fields) + listingPrivate/{id} (address, document URLs). 8. Best-effort notification to __admins__. | A1. Missing required field -> field-level error, submission blocked. A2. Description empty/whitespace or > 400 words -> blocked (150 words is a recommendation only). A3. < 4 photos -> blocked. A4. Missing either document -> blocked. A5. No valid showing window / end before start -> blocked. A6. Upload fails -> error, user can retry. | Pending listing (not public); exact address and document URLs only in listingPrivate/{id}; public doc has no address or document fields; admins notified (best effort). | TH-03 §3.1–3.2 (was: Build Instructions §2.1–2.3; Progress Report v1.1, P1) | v0.1 / v1.1 | Reported working (user, test project)
UC-07 | Edit a listing / resubmit after changes requested | Listing Intake | User (Owner) | FR-002, FR-003 | Owner has an existing listing. | 1. Open My Listings -> Edit. 2. Change fields/photos/documents/showing windows. 3. Save / resubmit. 4. If status was changes-requested, listing returns to pending. | A1. Edit breaks any intake rule -> same errors as creation (edit parity). A2. Non-owner opens edit URL -> denied. | Listing updated; resubmitted listing back in admin queue. | TH-03 §3.1–3.2 (was: Progress Report v1.1) | v1.1 | Unit tested (validation parity)
UC-08 | Set location with approximate map pin | Listing Map & Privacy | User (Owner) | FR-022 | Owner on create/edit listing. | 1. Type a location in map search. 2. Geocoder (with PH-specific retry) returns a pin. 3. Or click 'Use my exact address' to geocode the private address. 4. Adjust pin; save. 5. Public doc stores only a 5-char geohash marked approximate. | A1. Address not found -> message; owner can place pin manually. A2. Invalid coordinates -> rejected. A3. Pin optional -> listing saves without map. A4. OPEN BUG: 'Use my exact address' button not rendering in live browser. | Public listing has coarse location only; exact lat/long never public. | TH-03 §3.4; TH-02 §5 (was: Progress Report P2 Map; cleanup 2026-09-30) | v1.3+ | Implemented in source; open defect TC-MAP-003
UC-09 | View My Listings | Owner Listing Visibility | User (Owner) | FR-023 | Signed in; owns >= 0 listings. | 1. Open My Activity -> My Listings. 2. See card per listing: photo, city, type, bedrooms, price, verification status, review note, pending-request count. 3. View / Edit actions. 4. Tap request count -> Booking Requests tab filtered to that listing. | A1. No listings -> empty state with Create Listing CTA. A2. Request count fails to load -> 'unavailable' state (not zero). | Owner sees status of every listing; exact address/documents not shown. | TH-03 §10; TH-07 §2 (was: Progress Report P1 Owner visibility) | v1.3+ | Implemented in source
UC-10 | Review a pending listing | Admin Listing Review | Admin | FR-003 | Admin signed in; pending listing exists. | 1. Open Listing Review Queue (/admin/listings). 2. View photos, ownership document and government ID next to account name; use Download link for documents. 3. Check name match + document validity (plausibility only). 4. Choose Approve, Request changes (with note), or Reject (with note). 5. Owner is notified. | A1. KNOWN GAP (GAP-01): Cloudinary blocks PDF delivery (show_original_customer_untrusted); preview and Download fail. Do not make documents public as a workaround. A2. Queue load fails -> error + Retry. | Approved -> verified + verifiedAt, public with 'Verified – document reviewed' badge. Changes requested -> owner sees note. Rejected -> permanent. | TH-03 §3.3; TH-04 §6 (was: Build Instructions §2.2, §2.3; Build Plan §3) | v0.1 / v1.1 | Reported working; KNOWN GAP GAP-01 (PDF delivery)
UC-11 | Browse and filter verified listings | Search & Browse | Guest / User | FR-004 | Verified listings exist. | 1. Open Browse. 2. Apply city, price range, type filters. 3. Results sorted by Trust & Fairness Score by default. 4. Change sort. | A1. No matches -> empty state. A2. Pending/rejected/suspended listings never shown. | Filtered verified list displayed. | TH-03 §1, §7; TH-07 §2 (was: Build Instructions §3.1; Design Guide p.2) | v0.1 | Implemented in source
UC-12 | View listing details | Search & Browse | Guest / User | FR-004, FR-010, FR-022 | Listing is verified. | 1. Open a listing card. 2. See photos, Verified badge, price, trust score + cue, price-fairness label, availability/showing windows, reviews, approximate map, Request Booking CTA. | A1. No pin -> map hidden. A2. Guest clicks Request Booking -> prompted to sign in. A3. Pending listing URL opened by non-owner -> not found/denied. | Details displayed; no exact address or documents visible. | TH-03 §1, §7; TH-07 §2 (was: Design Guide p.3; Progress Report v1.3) | v0.1 / v1.3 | Implemented in source
UC-13 | View a public profile | Public Profile | Guest / User | FR-018 | Target user exists. | 1. Open owner's profile from listing. 2. See trust score, rating, Verified badge, founded-dispute flag (if count > 0). | A1. No founded disputes -> no warning. | Profile displayed; flag computed from Founded disputes. | TH-03 §6 (was: Design Guide p.11; Build Plan §6) | v0.3 | Implemented in source
UC-14 | Request a booking / viewing | Booking | User (Renter) | FR-005, FR-006 | Signed in, active; listing verified and purpose = rent; not the renter's own listing. | 1. On Listing Detail click Request Booking. 2. Select start/end date (within showing windows). 3. System checks overlap against Confirmed bookings only. 4. Create booking status Pending. 5. Owner notified. | A1. Overlap with Confirmed -> 'dates unavailable', no doc. A2. End before start / past date -> blocked. A3. Dates not selected -> button disabled with reason. A4. Pending overlaps are allowed (competing requests). A5. Suspended user -> blocked. A6. Sale listing -> no booking CTA; direct create denied. | Pending booking exists; owner has a notification. | TH-03 §4 (was: Build Instructions §3.1, §4; Build Plan §4) | v0.2 | Implemented in source
UC-15 | Confirm a booking request | Booking | User (Owner) | FR-005, FR-006 | Pending request on owner's listing. | 1. Open My Activity -> Booking Requests; review the day-number availability grid. 2. Click Approve. 3. Client queries Confirmed bookings scoped to the owner (ownerId == uid) for the listing and checks overlap. 4. Firestore transaction re-reads the request: exists, owned by this owner, still Pending -> status Confirmed + timestamps. 5. Renter notified (best effort). | A1. Overlap with an existing Confirmed booking -> approval refused. A2. Non-owner attempts confirm -> denied by rules. A3. Request no longer Pending (already handled) -> transaction aborts. A4. KNOWN GAP (GAP-02): overlap query runs before the transaction; two simultaneous approvals can both succeed. A5. KNOWN GAP (GAP-03): exact address is not copied to the booking by the current client path. | Booking Confirmed; range blocks future overlaps. | TH-03 §4.3, §4.6 (was: Build Instructions §4; Build Plan §4) | v0.2 | Reported working + emulator tested; KNOWN GAP GAP-02/03
UC-16 | Decline a pending request | Booking | User (Owner) | FR-005 | Pending request on owner's listing. | 1. Open Booking Requests. 2. Click Decline. 3. Pending booking document deleted (no 'Cancelled' status). | A1. Attempt to decline a Confirmed booking -> not allowed. | Request removed. | TH-03 §4 (was: Progress Report v1.2) | v1.2 | Implemented in source
UC-17 | Log deposit transaction reference | Deposit Accountability | User (Renter) | FR-007 | Renter's booking is Confirmed; deposit paid off-platform (GCash/bank). | 1. Open My Bookings -> booking. 2. Enter transaction reference. 3. Save; reference visible to renter and owner. | A1. Booking Pending -> field unavailable. A2. Empty reference -> validation error. A3. Owner or third party tries to write it -> denied. | depositReference stored on booking. | TH-03 §4.5 (was: Build Instructions §3.2) | v1.2 | Implemented in source
UC-18 | Mark a booking completed | Booking Completion | User (Renter) | FR-008 | Renter's booking is Confirmed. | 1. Open My Bookings. 2. Click Mark completed (renter is the single manual authority). 3. Status -> Completed; rating prompt shown. | A1. Owner side has no Mark completed button. A2. Pending booking cannot be completed. | Booking Completed; counts toward trust score. | TH-03 §4.4 (was: Progress Report P1 duplicate completion) | v1.2 / v1.3+ | Implemented in source
UC-19 | Auto-complete expired bookings | Scheduled Jobs | System (GitHub Actions, weekly) | FR-008 | Confirmed bookings with endDate < today. | 1. Weekly scrape.yml run executes scrape, then complete_expired_bookings.py. 2. Confirmed bookings with endDate < today -> Completed. 3. Trust-score recomputation runs next. (The daily Firebase scheduled function exists in source but is NOT deployed.) | A1. Non-expired or non-Confirmed bookings untouched. A2. Workflow failure -> visible in Actions history; manual re-run. | Expired bookings Completed. | TH-06 §3 (was: Build Plan §4; Progress Report v0.2) | v0.2 | Implemented in source (weekly Actions); Functions not deployed
UC-20 | View exact address after confirmation | Listing Map & Privacy | User (Renter) | FR-024 | Renter has a Confirmed booking. | 1. Open the confirmed booking. 2. Exact property address is shown (handoff from listingPrivate). | A1. Pending/declined booking -> address hidden. A2. Unrelated user -> denied. A3. KNOWN GAP (GAP-03): current client approval does not copy listingPrivate.address to the booking; the deployed-callable path that does is not active. | Renter sees exact address only after confirmation. | TH-03 §3.4; TH-02 §5 (was: Build Instructions §2.1; cleanup 2026-09-30) | v1.3+ | KNOWN GAP GAP-03
UC-21 | View My Activity | Navigation & Settings | User | FR-021 | Signed in. | 1. Open account menu -> My Activity. 2. Switch tabs: My Listings, My Bookings, Booking Requests (tab reflected in URL). | A1. Old direct routes still work. A2. New user -> empty states in each tab. | One entry point for all activity. | TH-03 §10; TH-07 §2 (was: Progress Report P2 Navigation) | v1.3+ | Implemented in source
UC-22 | Rate and review a completed booking | Ratings & Reviews | User (Renter / Owner) | FR-008 | Booking is Completed. | 1. Open rating prompt. 2. Select 1–5 score, optional comment. 3. Submit; review shows on listing. | A1. Booking not Completed -> denied. A2. Duplicate rating by same rater -> blocked. A3. Score outside 1–5 -> rejected. | Rating stored; trust score updated on next run. | TH-03 §5 (was: Build Instructions §4; Build Plan §2) | v0.2 | Unit tested
UC-23 | Raise a dispute | Disputes | User (Renter) | FR-009 | Renter's booking is Confirmed (or Completed, per agreed window). | 1. Open booking -> Raise Dispute. 2. Enter reason + evidence description. 3. Submit: dispute Open; booking prior status recorded; booking -> Disputed; dispute id linked. 4. Admins notified. | A1. Duplicate open dispute on same booking -> blocked. A2. Pending booking -> not allowed. A3. Empty reason -> validation. | Open dispute in admin queue; booking Disputed. | TH-03 §6 (was: Build Instructions §3.3; Progress Report P1 Dispute) | v0.3 / v1.3+ | Unit tested
UC-24 | Resolve a dispute | Disputes | Admin | FR-009 | Open dispute exists. | 1. Open Dispute Review Queue. 2. Review booking, reporter, reason, deposit reference. 3. Mark Founded or Dismissed with notes. 4. Reporter notified. | A1. Founded -> owner account + listing suspended, booking stays Disputed, public accountability count +1. A2. Dismissed -> booking restored to prior status, no flag. A3. Non-admin attempts -> denied. | Dispute closed with decision-maker, notes and resolvedAt. | TH-03 §6 (was: Build Instructions §3.3; Build Plan §6) | v0.3 / v1.3+ | Unit tested
UC-25 | Recompute trust scores | Trust & Fairness Score | System (GitHub Actions) | FR-010 | Verified listings, bookings, ratings exist. | 1. Weekly workflow runs bank_scraper/trust_scores.py (Admin SDK). 2. For each verified rental listing: booking score (Completed only, recency-weighted), rating score (avg/5), fairness score (price per m2 vs median of same city/type/price period, floor area within 20%). 3. trust = 0.4 booking + 0.4 rating + 0.2 fairness (0-1), displayed on a 5-point scale. 4. Write trustScores/{listingId} with label + computedAt. App reads the cache. | A1. No ratings -> no divide-by-zero. A2. No comparables -> 'Insufficient data'. A3. Sale listings excluded from rental fairness/trust comparisons. A4. JS (src/lib/trustScore.js) and Python formulas must stay in parity. | trustScores refreshed; Browse ordered by score. | TH-03 §7; TH-06 §3 (was: Build Plan §5) | v0.1–v1.3 | Unit tested
UC-26 | Flag repeated self-booking pattern | Anti-Gaming | System / Admin | FR-011 | Same renter–owner pair has completed bookings. | 1. Recompute detects >= 3 completed bookings for same pair within 30 days. 2. Set manualReviewRequired = true, selfBookingPatternCount. 3. Admin reviews. | A1. Only 2 in 30 days, or 3 spread over > 30 days -> no flag. | Suspicious listing flagged for manual review. | TH-03 §7.3 (was: Build Instructions §5; Progress Report v1.3) | v1.3 | Unit tested
UC-27 | View owner dashboard | Owner Dashboard | User (Owner) | FR-012 | Signed in. | 1. Open My Dashboard. 2. See listings, inquiries, pending requests, confirmed bookings, completed stays. | A1. New user -> zeros/empty state with CTA. | Counts match Firestore. | TH-03 §10 (was: Build Instructions §6 (#10); Design Guide p.12) | v1.3 | Implemented in source
UC-28 | View and manage notifications | Notifications | User | FR-013, FR-020 | Signed in. | 1. Bell shows unread count. 2. Open /notifications. 3. Mark one / all read. | A1. No notifications -> empty state. A2. Cannot read other users' notifications. A3. Notification write failure does not fail the main action. | Unread count accurate. | TH-03 §8 (was: Progress Report v1.3 Notifications) | v1.3 | Implemented in source
UC-29 | View admin notifications (listing submissions and disputes) | Notifications | Admin | FR-013, FR-020 | Admin signed in. | 1. Admin bell inside /admin/* shows __admins__ notifications: new listing submissions and disputes. 2. Open /admin/notifications; mark read (shared read state). | A1. Booking-request notices never appear in the admin feed (they go to the listing owner's personal feed). A2. Regular users cannot read the __admins__ feed. | Admin feed contains listing submissions and disputes only. | TH-03 §8 (was: Progress Report P0 Notification split) | v1.3+ | Implemented in source
UC-30 | Scrape Metrobank catalog | Bank Catalog | System (GitHub Actions) | FR-014 | FIREBASE_SERVICE_ACCOUNT secret set. | 1. Workflow writes key file from FIREBASE_SERVICE_ACCOUNT secret. 2. Scraper fetches Metrobank paginated JSON endpoint (page size 12, 2 s delay, retries). 3. Records need a reference number and finite price > 1. 4. Upserts bankProperties/metrobank_<ref> with merge, status active, firstSeen/lastSeen, keyword prefixes. 5. Previously active records not seen in this successful run -> delisted (never deleted). | A1. Zero valid records -> run fails closed; nothing delisted. A2. Layout/API change breaks scraper -> job fails, marketplace unaffected. A3. Secret never printed in logs. A4. Landbank (unverified) and BDO (placeholder) are not active sources. | Catalog current with lastSeen. | TH-06 §2; TH-03 §9 (was: Build Plan §7; Firebase Setup §10) | v0.1 | Unit tested (28 Python tests); no live benchmark
UC-31 | Browse bank-acquired catalog | Bank Catalog | Guest / User | FR-014 | bankProperties populated. | 1. Open Bank Catalog. 2. Filter by bank (Metrobank only exposed), city, keyword, price; sort; paginate; see result count. 3. Each card shows source link and 'last seen' date. | A1. Missing image -> fallback image. A2. No matches -> empty state. A3. Delisted properties hidden/marked. | Read-only catalog displayed. | TH-06 §2; TH-03 §9 (was: Build Plan §7; Design Guide p.7) | v0.1 | Implemented in source
UC-32 | Estimate loan amortization | Loan Calculator | Guest / User | FR-015 | On a bank property detail page. | 1. Price pre-filled. 2. Enter down payment %, annual rate, term years. 3. Monthly payment computed client-side. | A1. 0% rate -> P/n (no NaN). A2. Negative/empty inputs -> validation. A3. Down payment >= 100% -> validation or zero. | Estimate displayed. | TH-03 §9.1 (was: Build Plan §8) | v0.3 | Unit tested
UC-33 | Queue a bank-catalog refresh job | Admin Bank Catalog | Admin | FR-014, FR-016 | Admin signed in. | 1. Admin opens /admin/bank-catalog. 2. Selects bank(s) and queues a refresh -> scraperJobs/{id} created. 3. A trusted worker.py (polling every 15 s) processes the job and writes status/result fields. 4. Admin sees job status and last run. | A1. No trusted worker running -> job stays queued (UI must not show it as done). A2. Stale lastSeen reveals failed runs. A3. Non-admin cannot create jobs. | Admin knows catalog freshness. | TH-06 §3; TH-03 §9 (was: Design Guide p.20) | v0.1 | Implemented in source
UC-34 | Access the admin panel | Admin Access | Admin | FR-019 | Account exists. | 1. Navigate to /admin or a nested admin route. 2. Guard waits with visible status while profile loads. 3. Only role admin + status active renders admin routes. | A1. Regular user -> redirected. A2. Suspended -> suspended screen. A3. Missing/unreadable/incomplete profile -> fail closed with retry message. A4. Signed out -> login. | Only verified active admins see admin UI. | TH-03 §2; TH-02 §4 (was: Progress Report P0 Admin login) | v1.3+ | Unit tested (admin guard policy)
UC-35 | View admin dashboard | Admin Dashboard | Admin | FR-016 | Admin signed in. | 1. Open Admin Dashboard. 2. See pending-listing count, open-dispute count, recent activity. | A1. Load error -> message + Retry. | Counts match Firestore. | TH-03 §10 (was: Design Guide p.16; Progress Report v1.0) | v0.2 / v1.0 | Implemented in source
UC-36 | Suspend or reinstate a user | User Management | Admin | FR-016 | Admin signed in. | 1. Open User Management. 2. Suspend account (danger button, confirm). 3. Later reinstate. | A1. Suspended user cannot list, book, rate, or dispute. A2. Admin cannot suspend self (recommended check). | User status toggled. | TH-03 §10; TH-07 §4 (was: Design Guide p.19) | v0.2 | Implemented in source
UC-37 | Change appearance and accessibility settings | Navigation & Settings | User / Admin | FR-021 | Any user (signed in). | 1. Open Settings (/settings, or /admin/settings in admin layout). 2. Choose System/Light/Dark. 3. Toggle Larger text, High contrast, Reduce motion. 4. Reload -> preferences persist on this device. | A1. System mode follows OS preference changes. A2. Switch thumbs visible in dark mode. | Preferences applied and persisted. | TH-03 §10; TH-07 §2 (was: Progress Report P2 Settings; Design Guide B7) | v1.3+ | Implemented in source
UC-38 | Open retired Saved Searches URL | Saved Searches (Retired) | User | FR-017 (retired) | Legacy link or bookmark. | 1. Open /saved-searches. 2. Redirected to Browse. 3. Existing savedSearches records are not deleted. | A1. Menu no longer shows Saved Searches. | Safe redirect; data preserved. | TH-01 §5.2 (was: Progress Report cleanup 2026-09-30) | v1.3+ | Implemented in source
UC-39 | Seed synthetic demo data | Operations | Developer | NFR | Firebase Admin credentials available. | 1. Run seed_demo_data.py --dry-run. 2. Review counts. 3. Run seed_demo_data.py. | A1. No real IDs, passwords or Auth users created. A2. Placeholder documents labeled synthetic. | Demo dataset present. | TH-06 §4–6 (was: Progress Report v0.3 validation) | v0.3 | Implemented in source
UC-40 | Migrate legacy listing addresses | Operations | Developer / Admin | FR-022 | Verified Firestore backup (UC-43); maintenance window; dry-run output reviewed. | 1. Run migrate_listing_addresses.py (dry run default). 2. Inspect counts + conflicts. 3. Run with --apply. 4. Deploy rules and frontend. | A1. Re-run is idempotent. A2. Existing private addresses preserved. A3. Conflicting-owner records reported, not overwritten. | Public listings have no address field; addresses in listingPrivate. | TH-06 §4–6 (was: Progress Report P2 Map) | v1.3+ | Implemented in source; apply only after backup
UC-41 | Enforce data-access rules | Security (Firestore Rules) | System | NFR-SEC | Latest firestore.rules deployed. | 1. Every client read/write is evaluated by rules. 2. Deny-all fallback for unmatched paths. | A1. Direct SDK writes bypassing UI are denied when forbidden. | Data protected even against malicious clients. | TH-04 §3; TH-08 §6 (was: Firebase Setup §11; Progress Report backend readiness) | v0.1–v1.3 | Emulator tested (9 tests); rules deployed 2026-10-04
UC-42 | Recover from loading and runtime errors | Release Hardening | User / Admin | FR-016, NFR-REL | App running. | 1. Lazy routes show accessible loading fallback. 2. Runtime error -> top-level error screen with Reload. | A1. Slow network -> fallback, not blank page. | No blank screens. | TH-05 §6; TH-08 §8 (was: Progress Report v1.0) | v1.0 | Implemented in source
UC-43 | Back up Firestore | Operations | Developer (trusted) | NFR-OPS | Admin SDK credential from secret store; disk space outside repo. | 1. Run backup_firestore.py. 2. Every top-level collection written to timestamped JSONL (timestamps preserved) via temp file. 3. Record per-collection counts. | A1. Target backup already exists -> refuses to overwrite. A2. Credential missing -> fails before reading. | Verified, encrypted backup stored outside the repository. | TH-06 §4.1 | v1.3+ | Unit tested (fakes); no live rehearsal recorded
UC-44 | Restore Firestore (dry run first) | Operations | Developer (trusted) | NFR-OPS | Verified backup; NON-production target (emulator/test project) for rehearsal. | 1. Run restore_firestore.py <dir> (dry run): whole backup validated, no writes. 2. Review output. 3. Run with --apply: batches of 400. | A1. Invalid backup -> aborts before any write. A2. Records absent from backup are NOT deleted. A3. Never rehearse --apply on production. | Target matches backup for restored documents. | TH-06 §4.2 | v1.3+ | Unit tested (fakes); no live rehearsal recorded
UC-45 | Migrate verification documents to authenticated delivery | Operations | Developer / Admin | FR-028 | App can generate and consume short-lived authenticated URLs; backup verified. | 1. Run migrate_verification_documents.py (dry run default). 2. Review eligible assets. 3. --apply: rename assets to authenticated delivery, write listingPrivate.documents metadata, remove old URL fields only on success. | A1. Conversion fails -> old URL fields kept. A2. DO NOT APPLY to live until secure delivery path is deployed. | Documents no longer publicly deliverable. | TH-04 §6; TH-06 §5 | Roadmap | Roadmap — do not apply yet
UC-46 | Read legal and policy pages | Legal | Guest / User | NFR-LEGAL | None. | 1. Open footer link -> /legal/:documentId. 2. Read terms, privacy notice or disclaimers. | A1. Unknown documentId -> not-found message. | User can read the disclosed limitations. | TH-01 §5.3; TH-07 §5 | v1.3+ | Implemented in source
UC-47 | Process a queued scraper job | Admin Bank Catalog | System (trusted worker) | FR-026 | worker.py running with Admin SDK credential. | 1. Worker polls scraperJobs every 15 s. 2. Picks a queued job, runs the requested bank scrape. 3. Writes job status and result fields. | A1. Scrape fails -> job marked failed with reason; catalog unchanged. A2. Unsupported bank -> job fails clearly. | Job completed with result; catalog refreshed. | TH-06 §3 | v1.3+ | Implemented in source

## Test Cases
TC ID | UC ID | FR ID | Module | Title | Test Type | Priority | Preconditions | Test Steps | Test Data | Expected Result | Origin | Status | Actual Result | Tester | Date | Remarks
TC-AUTH-001 | UC-01 | FR-001 | Authentication | Register with valid email/password | Functional | High | Signed out | 1. Open Register. 2. Enter name, email, password. 3. Submit. | New email; password >= 6 chars | Account created; users/{uid} saved with role user, status active; redirected. | Existing (QA doc) | Passed (Dev) |  |  |  | Re-run on deployed build.
TC-AUTH-002 | UC-02 | FR-001 | Authentication | Login with wrong password | Negative | High | Registered account | 1. Open Login. 2. Enter registered email + wrong password. 3. Submit. | Registered test account | Inline error shown; no session created. | Existing (QA doc) | Passed (Dev)
TC-AUTH-003 | UC-03 | FR-001 | Authentication | Google sign-in creates profile on first login | Functional | High | Google sign-in enabled | 1. Click Continue with Google. 2. Pick account. | Google test account | Signed in; profile created on first sign-in only. | Existing (QA doc) | Passed (Dev)
TC-AUTH-004 | UC-01 | FR-001 | Authentication | Register with an email already in use | Negative | Medium | Account exists | 1. Register again with same email. | Existing email | Inline 'email already in use' error; no second profile. | New | Not Run
TC-AUTH-005 | UC-01 | FR-001 | Authentication | Register with weak password / invalid email | Negative | Medium | Signed out | 1. Enter 'abc' as password, or 'user@' as email. 2. Submit. | Invalid inputs | Inline field errors; submit blocked. | New | Not Run
TC-AUTH-006 | UC-02 | FR-001 | Authentication | Login with valid credentials | Functional | High | Registered account | 1. Enter valid email + password. 2. Submit. | Registered account | Signed in; account menu + bell visible; redirected. | New | Not Run |  |  |  | Mirrors acceptance criteria US-001.
TC-AUTH-007 | UC-02 | FR-016 | Authentication | Suspended account login | Negative | High | Account suspended by admin | 1. Log in as suspended user. 2. Try to create listing / book. | Suspended test user | Suspended-account screen/notice; protected actions blocked by UI and rules. | New | Not Run
TC-AUTH-008 | UC-04 | FR-001 | Authentication | Logout clears session | Functional | Medium | Signed in | 1. Log out. 2. Press browser Back. 3. Open /notifications directly. | Any user | Session cleared; protected pages redirect to login. | New | Not Run
TC-AUTH-009 | UC-03 | FR-001 | Authentication | Cancel Google popup | Negative | Low | Signed out | 1. Click Continue with Google. 2. Close popup. | - | Stays on login with no crash or infinite spinner. | New | Not Run
TC-AUTH-010 | UC-05 | FR-001 | Authentication | User cannot escalate own role/status | Security | High | Signed in as regular user | 1. Via SDK/console, update own users doc role='admin' or status='active' while suspended. | Regular user | Write denied by Firestore rules. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules. Previous note: Needs latest rules deployed (BUG-008).
TC-LIST-001 | UC-06 | FR-002 | Listing Intake | Submit a complete valid listing | Functional | High | Signed in | 1. Complete Create Listing. 2. Upload >=4 photos + both documents. 3. Add showing window. 4. Submit. | Valid listing data | Listing saved as pending; not in public search; appears in admin queue. | Existing (QA doc) | Passed (Dev) |  |  |  | User reported create + admin visibility working in test project (2026-10-04). Re-run on deployed build.
TC-INTAKE-001 | UC-06 | FR-002 | Listing Intake | Description length rules (updated) | Negative/Boundary | High | Otherwise valid listing | 1. Submit with empty/whitespace description. 2. Submit with 120 words. 3. Submit with 410 words. | Descriptions: blank, 120 words, 410 words | Blank -> blocked. 120 words -> ACCEPTED (150 is a recommendation hint only). 410 words -> blocked with inline guidance. | Updated | Not Run |  |  |  | Expected result changed by P1 description fix (was: 120 words blocked). Update QA doc Table 4 & FR-002.
TC-INTAKE-001B | UC-06 | FR-002 | Listing Intake | Description boundaries 1 / 400 / 401 words | Boundary | Medium | Otherwise valid listing | 1. Submit 1-word, 400-word, 401-word descriptions. | Generated text | 1 and 400 accepted; 401 blocked. | New | Not Run
TC-INTAKE-002 | UC-06 | FR-002 | Listing Intake | Fewer than 4 photos | Negative | High | Otherwise valid listing | 1. Upload 3 photos. 2. Submit. | 3 images | Blocked: minimum 4 photos. | Existing (QA doc) | Passed (Dev) |  |  |  | Unit test.
TC-INTAKE-003 | UC-06 | FR-003 | Listing Intake | Missing government ID or ownership document | Negative | High | Otherwise valid listing | 1. Upload only ownership doc; submit. 2. Upload only gov ID; submit. | One document each | Both blocked until both documents are uploaded. | Existing (QA doc) | Passed (Dev)
TC-INTAKE-004 | UC-06 | FR-002 | Listing Intake | Invalid or missing showing window | Negative | High | Otherwise valid listing | 1. Remove all windows. 2. Enter end time before start time. | Window 14:00–10:00 | Blocked: at least one valid window required. | Existing (QA doc) | Passed (Dev)
TC-INTAKE-005 | UC-07 | FR-003 | Listing Intake | Request changes then resubmit | Functional | High | Pending listing | 1. Admin selects Request changes with note. 2. Owner opens My Listings, sees note. 3. Edits and resubmits. | Pending listing | Owner sees changes-requested + note; resubmission returns listing to pending. | Existing (QA doc) | Passed (Dev)
TC-INTAKE-006 | UC-07 | FR-002 | Listing Intake | Edit parity with creation rules | Negative | High | Existing listing | 1. Edit listing; reduce to 2 photos / blank description. 2. Save. | Existing listing | Same validation errors as creation; not saved. | Existing (QA doc) | Passed (Dev)
TC-INTAKE-007 | UC-06 | FR-002 | Listing Intake | Each required field missing | Negative | High | Create Listing form | 1. For each of type, address/area, city, bedrooms, bathrooms, size, rent, availability date, amenities: leave blank and submit. | Otherwise valid listing | Field-level inline error under the missing field; no listing doc created. | New | Not Run |  |  |  | Data-driven: 9 iterations.
TC-INTAKE-008 | UC-06 | FR-002 | Listing Intake | Numeric field validation | Negative/Boundary | Medium | Create Listing form | 1. Enter 0 / negative / non-numeric for rent, size, bedrooms, bathrooms. | -1, 0, 'abc' | Rejected with inline error. | New | Not Run
TC-INTAKE-009 | UC-06 | FR-002 | Listing Intake | Non-image or oversized photo upload | Negative | Medium | Create Listing form | 1. Upload a .exe/.txt as photo. 2. Upload very large image. | Invalid files | Rejected with clear message; no broken URL saved. | New | Not Run
TC-INTAKE-010 | UC-06 | FR-003 | Listing Intake | Upload failure feedback | Negative | Medium | Create Listing form | 1. Go offline during photo/document upload. | DevTools offline | Error shown with retry; submit stays blocked until upload succeeds. | New | Not Run |  |  |  | Design Guide B8 feedback rule.
TC-INTAKE-011 | UC-06 | FR-002 | Listing Intake | Multi-step form progress indicator | UI | Low | Create Listing form | 1. Walk through details -> photos -> documents steps. | - | Progress indicator shown; data kept when moving back/forward. | New | Not Run |  |  |  | Design Guide B8.
TC-INTAKE-012 | UC-06 | FR-003 | Listing Intake | Limitation copy shown | UI | Medium | Create Listing / Listing Detail | 1. Read verification copy. | - | UI states review is a document-plausibility check, not a legal title search. | New | Not Run |  |  |  | Build Instructions §7.
TC-INTAKE-013 | UC-07 | FR-002 | Listing Intake | Non-owner cannot edit listing | Security | High | Listing owned by user A | 1. As user B open /listings/{id}/edit. 2. Attempt direct update. | Two users | UI denies; Firestore update denied. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules. Previous note: Needs rules deploy.
TC-INTAKE-014 | UC-06 | FR-003 | Listing Intake | PDF documents upload as raw resource | Functional | Medium | Create Listing form | 1. Upload a PDF ownership document. 2. Inspect stored URL/resource type. | Small PDF | Upload succeeds as Cloudinary raw resource in listing-specific folder; URL stored only in listingPrivate. | New | Not Run |  |  |  | TH-03 §3.2.
TC-INTAKE-015 | UC-06 | FR-002 | Listing Intake | Purpose and rental term | Functional | Medium | Create Listing form | 1. Choose purpose Sale. 2. Choose purpose Rent without rental term. | - | Sale accepted without booking fields; Rent requires rental term/price period. | New | Not Run |  |  |  | Confirm exact field names in listingValidation.js.
TC-VER-001 | UC-10 | FR-003 | Admin Listing Review | Approve a pending listing | Functional | High | Admin; pending listing | 1. Open Listing Review Queue. 2. Approve. | Seeded pending listing | verified + verifiedAt; appears in search with 'Verified – document reviewed' badge; owner notified. | Existing (QA doc) | Passed (Dev) |  |  |  | Approval path reported working (2026-10-04). Image rendering fixed (BUG-002); PDF delivery see TC-VER-004.
TC-VER-002 | UC-41 | FR-003 | Admin Listing Review | Signed-out read of pending listing | Security | High | Pending listing | 1. Sign out. 2. Read pending listing by ID. | Pending listing ID | Read denied. | Existing (QA doc) | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules. Previous note: BUG-008.
TC-VER-003 | UC-10 | FR-003 | Admin Listing Review | Reject a listing with note | Functional | High | Admin; pending listing | 1. Reject with reason. | Pending listing | Status rejected; owner sees reason and is notified; never public. | New | Not Run
TC-VER-004 | UC-10 | FR-003 | Admin Listing Review | Queue shows both documents + account name | Functional | High | Pending listing with photo + PDF docs | 1. Open item in queue. | JPG ID + PDF deed | Photos, ownership doc and gov ID viewable next to account name. | New | Failed | Photos and image IDs render; PDF ownership document blocked by Cloudinary: show_original_customer_untrusted. |  | 2026-10-04 | KNOWN GAP GAP-01 (account-level Cloudinary block). Do not make documents public to work around it.
TC-VER-005 | UC-10 | FR-003 | Admin Listing Review | Non-admin cannot approve | Security | High | Regular user | 1. Direct write verificationStatus='verified' on own listing. | Own pending listing | Write denied. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules. Previous note: Needs rules deploy.
TC-VER-006 | UC-10 | FR-003 | Admin Listing Review | Document URLs not in public Firestore data | Security | High | Verified listing | 1. As guest, open listing detail and inspect network/page source. | Verified listing | No ownership/ID document URLs in public data. | New | Not Run |  |  |  | Covers Firestore only (documents live in listingPrivate). File-level privacy is TC-VER-008.
TC-VER-007 | UC-10 | FR-003 | Admin Listing Review | Empty review queue state | UI | Low | No pending listings | 1. Open queue. | - | Empty-state message, no error. | New | Not Run
TC-VER-008 | UC-10 | FR-028 | Admin Listing Review | Verification file not fetchable without authorization | Security | Critical | Listing with uploaded ID | 1. Copy document URL as admin. 2. Open it in a signed-out private window. | - | File is NOT delivered to an unauthenticated request. | New | Failed | Unsigned-preset delivery URLs are public if known (Cloudinary). |  | 2026-10-04 | KNOWN GAP GAP-01. Exit: authenticated delivery with short-lived signed URLs (TH-04 §6).
TC-VER-009 | UC-10 | FR-003 | Admin Listing Review | Admin Download link for documents | Functional | High | Admin; pending listing with PDF | 1. Click Download on the ownership document. | PDF document | Document downloads for the admin. | New | Failed | Blocked by Cloudinary show_original_customer_untrusted; attachment flag cannot bypass account-level block. |  | 2026-10-04 | GAP-01. Download UI also not confirmed on deployed hosting.
TC-SRCH-001 | UC-11 | FR-004 | Search & Browse | Filter by city, price, type | Functional | High | Seeded listings | 1. Open Browse. 2. Apply filters. | Several cities | Only verified matches shown; empty state when none. | Existing (QA doc) | Passed (Dev)
TC-SRCH-002 | UC-11 | FR-010 | Search & Browse | Default sort by trust score | Integration | High | Workflow run | 1. Run workflow. 2. Check computedAt. 3. Open Browse. | Seeded bookings/ratings | Listings ordered by score, differing from price/recency sort. | Existing (QA doc) | Passed (Dev)
TC-SRCH-003 | UC-11 | FR-004 | Search & Browse | Pending/rejected/suspended listings excluded | Functional | High | Mixed statuses seeded | 1. Browse without filters. | Mixed listings | Only verified, non-suspended listings shown. | New | Not Run
TC-SRCH-004 | UC-11 | FR-004 | Search & Browse | Price range boundaries | Boundary | Medium | Seeded listings | 1. Set min=max=exact price of one listing. 2. Set min > max. | Known prices | Inclusive match; invalid range handled with message. | New | Not Run
TC-SRCH-005 | UC-12 | FR-004 | Search & Browse | Listing detail content above the fold | UI | Medium | Verified listing | 1. Open listing at 390 px. | - | Verified badge + trust score visible without scrolling; Request Booking is the dominant CTA. | New | Not Run |  |  |  | Design Guide Part C.
TC-SRCH-006 | UC-12 | FR-001 | Search & Browse | Guest clicks Request Booking | Functional | Medium | Signed out | 1. Open listing. 2. Click Request Booking. | - | Prompted to sign in; returns to listing after login. | New | Not Run
TC-SRCH-007 | UC-12 | FR-004 | Search & Browse | Home shows live verified listings only | Functional | Low | - | 1. Open Home. | - | Rental showcase uses verified live listings; no sample cards. | New | Not Run |  |  |  | P2 navigation change.
TC-SRCH-008 | UC-11 | FR-004 | Search & Browse | Filter by listing purpose | Functional | Medium | Rent and sale listings seeded | 1. Filter purpose = Rent. 2. Filter purpose = Sale. | - | Only matching verified listings shown; sale cards have no booking CTA. | New | Not Run
TC-BOOK-001 | UC-14 | FR-005 | Booking | Request free dates | Functional | High | Renter signed in | 1. Open verified listing. 2. Request free dates. | No Confirmed booking on Jan 5–8 | Booking Pending; owner sees request. | Existing (QA doc) | Passed (Dev)
TC-BOOK-002 | UC-14 | FR-006 | Booking | Overlap with Confirmed booking rejected | Negative | High | Confirmed Dec 10–15 | 1. Request Dec 12–18. | Seeded Confirmed booking | 'Dates unavailable'; no document created. | Existing (QA doc) | Passed (Dev)
TC-BOOK-003 | UC-15 | FR-006 | Booking | First confirmation wins (sequential approvals) | Functional | High | Two Pending same dates | 1. Owner confirms first. 2. Owner confirms second. | Two renters | Second confirmation rejected by confirm-time check. | Existing (QA doc) | Passed (Dev) |  |  |  | Covers sequential approvals only. Simultaneous approvals: TC-BOOK-019 (GAP-02).
TC-BOOK-004 | UC-41 | FR-005 | Booking | Forbidden status 'Cancelled' by direct write | Security | High | Pending booking | 1. Direct write status='Cancelled'. | Pending booking | Denied; only 4 statuses allowed. | Existing (QA doc) | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules. Previous note: BUG-008.
TC-BOOK-005 | UC-16 | FR-005 | Booking | Decline pending request | Functional | High | Pending booking | 1. Owner declines. | Pending booking | Request removed; no forbidden status written. | Existing (QA doc) | Passed (Dev)
TC-BOOK-006 | UC-17 | FR-007 | Booking | Log deposit reference | Functional | High | Confirmed booking | 1. Renter enters GCash ref. 2. Save. | GC-TEST-0001 | Stored and visible to both; unavailable on Pending. | Existing (QA doc) | Passed (Dev)
TC-BOOK-007 | UC-18 | FR-008 | Booking | Renter marks booking completed (updated) | Functional | High | Confirmed booking | 1. Renter clicks Mark completed. | Confirmed booking | Completed once; rating prompt appears; dispute eligibility preserved. | Updated | Not Run |  |  |  | Was 'renter or owner'; owner button removed (P1). Renter is the only manual authority.
TC-BOOK-008 | UC-18 | FR-008 | Booking | Owner has no Mark completed action | Functional | High | Owner with Confirmed booking | 1. Open Booking Requests as owner. | Confirmed booking | No Mark completed button on owner side. | New | Not Run |  |  |  | P1 duplicate completion.
TC-BOOK-009 | UC-14 | FR-006 | Booking | Adjacent date ranges (boundary) | Boundary | High | Confirmed Dec 10–15 | 1. Request Dec 15–18. 2. Request Dec 5–10. | Seeded Confirmed | Allowed (start < end && end > start rule; touching edges do not overlap). | New | Not Run |  |  |  | Confirm team's intended inclusive/exclusive rule.
TC-BOOK-010 | UC-14 | FR-006 | Booking | Range fully containing a Confirmed booking | Negative | High | Confirmed Dec 10–15 | 1. Request Dec 1–31. | Seeded Confirmed | Rejected. | New | Not Run
TC-BOOK-011 | UC-14 | FR-006 | Booking | Pending requests do not block each other | Functional | Medium | Existing Pending Dec 10–15 | 1. Second renter requests Dec 10–15. | Two renters | Second request created as Pending. | New | Not Run |  |  |  | Build Plan §4.
TC-BOOK-012 | UC-14 | FR-005 | Booking | Invalid dates | Negative | High | Renter | 1. End before start. 2. Start in the past. 3. No dates. | - | Blocked; Request button disabled with reason when no dates. | New | Not Run
TC-BOOK-013 | UC-14 | FR-005 | Booking | Owner cannot book own listing | Negative | Medium | Owner signed in | 1. Request booking on own listing. | Own listing | Blocked (UI + rules). | New | Not Run |  |  |  | Confirm intended behavior.
TC-BOOK-014 | UC-14 | FR-005 | Booking | Booking a non-verified listing | Security | High | Pending listing ID | 1. Direct create booking on pending listing. | Pending listing | Denied. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules. Previous note: Needs rules deploy.
TC-BOOK-015 | UC-17 | FR-007 | Booking | Deposit reference on Pending / empty / by owner | Negative | High | Pending & Confirmed bookings | 1. Try on Pending. 2. Save empty. 3. Owner writes depositReference directly. | - | All rejected. | New | Not Run
TC-BOOK-016 | UC-18 | FR-008 | Booking | Completing a Pending booking | Negative | Medium | Pending booking | 1. Direct write status='Completed'. | Pending booking | Denied. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules. Previous note: Needs rules deploy.
TC-BOOK-017 | UC-14 | FR-005 | Booking | Request outside showing windows | Negative | Medium | Listing with Sat 9–12 window | 1. Request Monday 15:00. | Seeded windows | Blocked or warned per spec. | New | Not Run |  |  |  | Confirm expected behavior.
TC-BOOK-018 | UC-14 | FR-013 | Booking | Booking still succeeds if notification write fails | Reliability | Medium | Renter | 1. Force notification write failure. 2. Submit request. | Test build / rules | Booking created; failure logged, not shown as booking failure. | New | Not Run |  |  |  | Best-effort notifications.
TC-BOOK-019 | UC-15 | FR-006 | Booking | Concurrent approvals of overlapping requests | Concurrency | Critical | Two Pending overlapping requests | 1. In the emulator, run two owner approval flows in parallel (Promise.all). | Two renters, same dates | Exactly one becomes Confirmed; the other is refused. | New | Not Run |  |  |  | KNOWN GAP GAP-02: overlap query runs outside the transaction — expected to fail until TH-03 §4.6 option A/B is implemented.
TC-BOOK-020 | UC-14 | FR-025 | Booking | Sale listing is not bookable | Negative | High | Verified sale listing | 1. Open detail. 2. Direct create booking for it. | Sale listing | No Request Booking CTA; direct create denied. | New | Not Run
TC-BOOK-021 | UC-15 | FR-005 | Booking | Owner approval rule: Pending -> Confirmed only | Security | High | Emulator | 1. Owner updates Pending -> Confirmed. 2. Owner changes other fields / other statuses. 3. Non-owner attempts. | - | Step 1 allowed; steps 2-3 denied. | New | Passed (Dev) | Owner approval case passed in emulator suite (9 tests). |  |  | scripts/firestore-rules-smoke.mjs. Re-run on live rules.
TC-BOOK-022 | UC-15 | FR-005 | Booking | Owner-scoped Confirmed-bookings query allowed | Security | High | Emulator | 1. Owner queries bookings where ownerId == uid and status == Confirmed. | - | Query allowed; unscoped query denied. | New | Passed (Dev) | Owner-scoped query case passed in emulator suite. |  |  | Emulator only.
TC-BOOK-023 | UC-15 | FR-005 | Booking | Owner approves a pending request (happy path) | Functional | High | Pending request, no overlap | 1. Owner opens Booking Requests. 2. Approves. | - | Status Confirmed; renter notified; dates blocked for new requests. | New | Passed (Dev) | User reported owner approval working in test project. |  | 2026-10-04 | Browser-reported; re-run on deployed build.
TC-JOB-001 | UC-19 | FR-008 | Ratings & Completion | Expired Confirmed booking auto-completes | Integration | High | Expired Confirmed booking | 1. Run workflow. 2. Check booking. | Seeded | Status Completed. | Existing (QA doc) | Passed (Dev) |  |  |  | Runs via weekly GitHub Actions (complete_expired_bookings.py). Firebase scheduled function not deployed.
TC-JOB-002 | UC-19 | FR-008 | Ratings & Completion | Non-expired or non-Confirmed untouched | Integration | Medium | Mixed bookings | 1. Run job. | Future Confirmed, expired Pending, Disputed | None changed. | New | Not Run
TC-JOB-003 | UC-19 | FR-008 | Ratings & Completion | Job cadence acceptable | Integration | Low | Workflow schedule | 1. Check scrape.yml cron. | - | scrape.yml cron documented as weekly; team decision recorded (keep weekly or move to daily). | New | Not Run |  |  |  | P1 finding.
TC-RATE-001 | UC-22 | FR-008 | Ratings & Completion | Rate a completed booking | Functional | Medium | Completed booking | 1. Submit 1–5 + comment. | Completed booking | Rating saved; shown on listing reviews. | Existing (QA doc) | Passed (Dev)
TC-RATE-002 | UC-22 | FR-008 | Ratings & Completion | Rating on Pending booking by direct write | Security | High | Pending booking | 1. Direct write rating. | Pending booking | Denied. | Existing (QA doc) | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules. Previous note: BUG-008.
TC-RATE-003 | UC-22 | FR-008 | Ratings & Completion | Score outside 1–5 | Negative | Medium | Completed booking | 1. Submit 0 or 6. | 0, 6 | Rejected. | New | Not Run
TC-RATE-004 | UC-22 | FR-008 | Ratings & Completion | Duplicate rating by same rater | Negative | Medium | Already rated | 1. Rate again. | - | Blocked. | New | Not Run |  |  |  | Max 2 ratings per booking.
TC-RATE-005 | UC-22 | FR-008 | Ratings & Completion | Non-participant rates booking | Security | Medium | Completed booking | 1. As unrelated user, direct write rating. | - | Denied. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-DISP-001 | UC-23 | FR-009 | Disputes | Raise a dispute (updated) | Functional | High | Confirmed booking | 1. Renter opens booking. 2. Raise Dispute with reason. | Seeded Confirmed | Dispute Open in admin queue; booking -> Disputed; prior status + dispute link stored; admins notified. | Updated | Not Run |  |  |  | Booking state now changes on submit (P1 dispute).
TC-DISP-002 | UC-24 | FR-009 | Disputes | Founded dispute | Functional | High | Open dispute | 1. Admin marks Founded with notes. | Open dispute | Owner account + listing suspended; booking stays Disputed; public flag shows; reporter notified. | Existing (QA doc) | Passed (Dev) |  |  |  | Re-run after P1 change.
TC-DISP-003 | UC-24 | FR-009 | Disputes | Dismissed dispute restores prior status (updated) | Functional | High | Open dispute on Confirmed booking | 1. Admin marks Dismissed. | Open dispute | No suspension/flag; booking restored to Confirmed; reporter notified. | Updated | Not Run |  |  |  | Restore behavior added in P1.
TC-DISP-004 | UC-23 | FR-009 | Disputes | Duplicate open dispute blocked | Negative | High | Open dispute exists | 1. Raise another dispute on same booking. | - | Blocked. | New | Not Run
TC-DISP-005 | UC-23 | FR-009 | Disputes | Dispute on Pending booking | Negative | Medium | Pending booking | 1. Try Raise Dispute. | - | Not allowed. | New | Not Run
TC-DISP-006 | UC-23 | FR-009 | Disputes | Empty dispute reason | Negative | Medium | Confirmed booking | 1. Submit blank reason. | - | Inline error. | New | Not Run
TC-DISP-007 | UC-24 | FR-009 | Disputes | Audit trail completeness | Functional | High | Resolved dispute | 1. Inspect dispute record. | - | Has bookingId, raisedBy, reason, decision, notes, resolver, createdAt, resolvedAt. | New | Not Run |  |  |  | P1 acceptance.
TC-DISP-008 | UC-24 | FR-009 | Disputes | Suspended owner's listings hidden | Integration | High | Founded dispute | 1. Browse as guest. | Suspended owner | Suspended listing no longer in search. | New | Not Run
TC-DISP-009 | UC-23 | FR-009 | Disputes | Dispute on Completed booking within window | Functional | Medium | Completed booking | 1. Raise dispute. | - | Allowed/blocked per agreed time window. | New | Not Run |  |  |  | Policy pending approval (Release QA #3).
TC-PROF-001 | UC-13 | FR-018 | Public Profile | Flagged owner profile | Functional | Medium | Owner with 1 Founded | 1. Open public profile. | Seeded | Shows trust score, rating, '1 founded dispute' warning. | Existing (QA doc) | Passed (Dev)
TC-PROF-002 | UC-13 | FR-018 | Public Profile | Dismissed disputes don't flag | Functional | Medium | Owner with only Dismissed | 1. Open profile. | - | No warning shown. | New | Not Run
TC-TRUST-001 | UC-25 | FR-010 | Trust & Fairness Score | Score formula matches hand calculation | Unit | High | Seed data | 1. Run score functions. 2. Compare with manual calc. | Seed data | Sub-scores and total match. | Existing (QA doc) | Passed (Dev)
TC-TRUST-002 | UC-25 | FR-010 | Trust & Fairness Score | Only Completed bookings count | Unit | High | Seed listing | 1. Add Pending + Completed. 2. Recompute. | - | Only Completed affects booking score. | Existing (QA doc) | Passed (Dev)
TC-TRUST-003 | UC-25 | FR-010 | Trust & Fairness Score | Recency weighting | Unit | Medium | Completed bookings 2 and 8 months ago | 1. Compute booking score. | - | 1.0 + 0.5 = 1.5. | New | Not Run |  |  |  | Build Plan §5.
TC-TRUST-004 | UC-25 | FR-010 | Trust & Fairness Score | No ratings - no NaN | Unit | High | Listing without ratings | 1. Recompute. | - | Rating score 0/default; total is a valid number. | New | Not Run
TC-TRUST-005 | UC-12 | FR-010 | Trust & Fairness Score | Trust score display with cue | UI | Low | Verified listing | 1. Open listing detail. | - | Numeric score + plain-language cue shown. | New | Not Run |  |  |  | Design Guide B5.
TC-FAIR-001 | UC-25 | FR-010 | Trust & Fairness Score | Above/At/Below market labels | Unit/Integration | High | Comparables seeded | 1. Recompute for listings at +20%, 0%, -20% vs median. | Seeded | Above market / At market / Below market. | Existing (QA doc) | Not Run
TC-FAIR-002 | UC-25 | FR-010 | Trust & Fairness Score | Insufficient data | Unit | High | No comparables | 1. Recompute. | Isolated listing | 'Insufficient data'. | Existing (QA doc) | Not Run
TC-FAIR-003 | UC-26 | FR-011 | Trust & Fairness Score | Self-booking pattern flagged | Integration | High | 3 completed in 30 days, same pair | 1. Run workflow. | Synthetic | manualReviewRequired=true; selfBookingPatternCount=3. | Existing (QA doc) | Not Run
TC-FAIR-004 | UC-25 | FR-010 | Trust & Fairness Score | ±15% threshold boundaries | Boundary | Medium | Comparables | 1. Compute at +15%, +15.1%, -15%, -15.1%. | - | ±15% = At market; beyond = Above/Below. | New | Not Run
TC-FAIR-005 | UC-25 | FR-010 | Trust & Fairness Score | 20% size band filter | Unit | Medium | Comparables of varied size | 1. Include 25% larger listing. | - | Excluded from median. | New | Not Run
TC-FAIR-006 | UC-26 | FR-011 | Trust & Fairness Score | No flag below threshold | Unit | Medium | 2 bookings in 30 days, or 3 over 45 days | 1. Recompute. | - | manualReviewRequired=false. | New | Not Run
TC-TRUST-006 | UC-25 | FR-010 | Trust & Fairness Score | JS / Python formula parity | Unit | High | Shared fixture | 1. Run trustScore.js and trust_scores.py on the same fixture. | Shared JSON fixture | Identical scores and labels (within rounding). | New | Not Run |  |  |  | TH-03 §7.4.
TC-FAIR-007 | UC-25 | FR-010 | Trust & Fairness Score | Sale listings excluded from comparables | Unit | Medium | Sale + rent listings same city/type | 1. Recompute. | - | Sale listings excluded from median and not scored as rentals. | New | Not Run
TC-FAIR-008 | UC-25 | FR-010 | Trust & Fairness Score | Different price period excluded | Unit | Medium | Monthly and nightly listings | 1. Recompute. | - | Only same price period used as comparables. | New | Not Run
TC-DASH-001 | UC-27 | FR-012 | Owner Dashboard & My Listings | Dashboard counts match Firestore | Functional | Low | Seeded owner | 1. Open My Dashboard at 390 px. | Seeded | Counts match. | Existing (QA doc) | Not Run
TC-DASH-002 | UC-27 | FR-012 | Owner Dashboard & My Listings | New user dashboard | UI | Low | New account | 1. Open dashboard. | - | Zeros/empty state with CTA. | New | Not Run
TC-MYL-001 | UC-09 | FR-023 | Owner Dashboard & My Listings | Listing cards show key details | Functional | Medium | Owner with multiple listings | 1. Open My Listings. | Mixed statuses | Photo, city, type, bedrooms, price, status, review note, View/Edit on each card. | New | Not Run
TC-MYL-002 | UC-09 | FR-023 | Owner Dashboard & My Listings | Per-listing pending counts | Functional | Medium | Listings with 0 and 2 pending | 1. Open My Listings. | - | Correct counts per listing. | New | Not Run
TC-MYL-003 | UC-09 | FR-023 | Owner Dashboard & My Listings | Count load failure is not zero | Negative | Medium | Owner | 1. Block bookings query. 2. Open My Listings. | DevTools | 'Unavailable' state, not 0. | New | Not Run
TC-MYL-004 | UC-09 | FR-023 | Owner Dashboard & My Listings | Request link filters by listing | Functional | Medium | Listing with requests | 1. Tap request count. 2. Tap 'all requests'. | - | Booking Requests tab filtered; back link shows all. | New | Not Run
TC-MYL-005 | UC-09 | FR-023 | Owner Dashboard & My Listings | Private data excluded | Security | High | Owner | 1. Inspect My Listings. | - | No exact address or document URLs on cards. | New | Not Run
TC-MYL-006 | UC-09 | FR-023 | Owner Dashboard & My Listings | Narrow viewport layout | UI | Low | Owner | 1. View at 360/390 px. | - | Cards readable, no overflow. | New | Not Run
TC-NOTIF-001 | UC-28 | FR-013 | Notifications | Owner notified of booking request | Functional | High | Renter + owner | 1. Renter requests. 2. Owner opens bell. 3. Mark read. | - | Unread notification; count clears. | Existing (QA doc) | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules. Previous note: BUG-008.
TC-NOTIF-002 | UC-28 | FR-013 | Notifications | Renter notified of confirmation | Functional | High | Renter + owner | 1. Owner confirms. 2. Renter checks bell. | - | Confirmation notification received. | Existing (QA doc) | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-NOTIF-003 | UC-29 | FR-013 | Notifications | Dispute notifications | Functional | High | Renter + admin | 1. Raise dispute. 2. Admin resolves. | - | Admins notified on dispute submission; reporter notified on resolution. | Existing (QA doc) | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-NOTIF-004 | UC-41 | FR-013 | Notifications | Cross-user notification access | Security | High | Two users | 1. As A read/create B's notifications. | - | Denied. | Existing (QA doc) | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-NOTIF-005 | UC-29 | FR-020 | Notifications | Admin feed: listing submissions and disputes only | Functional | High | Admin who also owns listings | 1. Submit a new listing. 2. Create a booking request on the admin's own listing. 3. Raise a dispute. 4. Open the admin bell under /admin. | - | Admin inbox shows the listing submission and the dispute; the booking request appears only in the admin's personal user feed. | Updated | Not Run |  |  |  | Updated 2026-10-04: admin broadcast covers listing submissions AND disputes (FR-020 revised).
TC-NOTIF-006 | UC-29 | FR-020 | Notifications | No booking-request broadcast to __admins__ | Security | High | Regular user | 1. Direct create notification to __admins__ with type booking-request. | - | Denied. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-NOTIF-007 | UC-29 | FR-020 | Notifications | Regular user cannot read admin feed | Security | High | Regular user | 1. Query __admins__ notifications. | - | Denied. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-NOTIF-008 | UC-29 | FR-020 | Notifications | Legacy admin booking notices hidden | Functional | Medium | Old booking-request docs in __admins__ | 1. Open admin inbox. | Legacy data | Filtered out; not readable after rules deploy. | New | Not Run
TC-NOTIF-009 | UC-29 | FR-020 | Notifications | Admins cannot create arbitrary broadcasts | Security | Medium | Admin | 1. Direct create notification to __admins__. | - | Denied for types other than those the rules allow (listing submission, dispute). | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-NOTIF-010 | UC-28 | FR-013 | Notifications | Mark all read / empty inbox | Functional | Low | User | 1. Mark all read. 2. New user opens inbox. | - | Count 0; empty state shown. | New | Not Run
TC-NOTIF-011 | UC-28 | FR-013 | Notifications | Listing decision notification | Functional | Medium | Owner | 1. Admin approves/requests changes/rejects. | - | Owner notified for each decision. | New | Not Run
TC-NOTIF-012 | UC-06 | FR-020 | Notifications | New listing notifies admins | Functional | High | Owner + admin | 1. Submit a listing. 2. Open admin bell. | - | Listing-submission notification in __admins__ feed linking to review item; submission succeeds even if notification fails. | New | Not Run
TC-MAP-001 | UC-08 | FR-022 | Listing Map & Privacy | Search address and place pin | Functional | Medium | Create/Edit listing | 1. Type 'Santa Rosa, Laguna'. 2. Select result. | PH address | Pin placed; attribution shown. | New | Not Run
TC-MAP-002 | UC-08 | FR-022 | Listing Map & Privacy | PH-specific geocoder retry | Functional | Low | - | 1. Enter full street address without 'Philippines'. | Full address | Resolves via PH retry. | New | Not Run
TC-MAP-003 | UC-08 | FR-022 | Listing Map & Privacy | 'Use my exact address' shortcut renders | Functional / Regression | High | Private address prefilled | 1. Open edit listing with address. 2. Hard reload (clear cache). 3. Check map search box. | Listing with address | Button visible; clicking geocodes private address and places pin. | New | Failed |  |  |  | OPEN BUG: button not rendering in live browser (Release QA #11–12).
TC-MAP-004 | UC-08 | FR-022 | Listing Map & Privacy | Public doc stores only 5-char geohash | Security | High | Listing with pin | 1. Inspect public listing doc. | - | Only geohash (5 chars) + approximate flag; no lat/long, no address. | New | Not Run
TC-MAP-005 | UC-08 | FR-022 | Listing Map & Privacy | Invalid pin rejected | Negative | Medium | - | 1. Direct write lat/long or 7-char geohash to listing. | - | Denied by rules. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-MAP-006 | UC-12 | FR-022 | Listing Map & Privacy | Legacy listing without pin | Regression | Medium | Old listing | 1. Open detail. | - | Map section hidden; page works. | New | Not Run
TC-MAP-007 | UC-41 | FR-022 | Listing Map & Privacy | listingPrivate access | Security | High | Listing | 1. As guest/other user read listingPrivate/{id}. 2. As owner/admin read. | - | Others denied; owner/admin allowed. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-MAP-008 | UC-06 | FR-022 | Listing Map & Privacy | New listing cannot contain public address | Security | High | - | 1. Direct create listing with address field. | - | Denied. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-MAP-009 | UC-20 | FR-024 | Listing Map & Privacy | Exact address after confirmation | Functional | High | Confirmed booking | 1. Renter opens confirmed booking. | - | Exact address shown. | New | Not Run |  |  |  | KNOWN GAP GAP-03: current client approval does not copy listingPrivate.address to the booking. Expected to fail until fixed.
TC-MAP-010 | UC-20 | FR-024 | Listing Map & Privacy | Exact address hidden before confirmation | Security | High | Pending booking / unrelated user | 1. Open booking / query address. | - | Address not shown/denied. | New | Not Run
TC-MAP-011 | UC-40 | FR-022 | Listing Map & Privacy | Migration dry run | Functional | High | Backup taken | 1. Run migrate_listing_addresses.py. | Live project | Counts reported; no writes. | New | Not Run |  |  |  | Take and verify a backup first (TC-OPS-001). Dry run only until reviewed.
TC-MAP-012 | UC-40 | FR-022 | Listing Map & Privacy | Migration apply is idempotent | Functional | High | Dry run reviewed | 1. Run --apply twice. | - | Second run changes nothing; existing private addresses kept; conflicts reported. | New | Not Run
TC-NAV-001 | UC-21 | FR-021 | Navigation & Settings | Account menu has no duplicates | UI | Medium | Signed in | 1. Open account menu. | - | Single My Activity entry; no Saved Searches. | New | Not Run
TC-NAV-002 | UC-21 | FR-021 | Navigation & Settings | My Activity tabs + URL | Functional | Medium | Signed in | 1. Switch each tab. 2. Reload. 3. Copy URL to new tab. | - | Tab state in URL and restored. | New | Not Run
TC-NAV-003 | UC-21 | FR-021 | Navigation & Settings | Old direct routes still work | Regression | Low | - | 1. Open previous My Bookings / Requests routes. | - | Pages load. | New | Not Run
TC-NAV-004 | UC-38 | FR-017 | Navigation & Settings | /saved-searches redirects | Regression | Low | Existing savedSearches docs | 1. Open /saved-searches. | - | Redirect to Browse; records remain in Firestore. | New | Not Run
TC-SET-001 | UC-37 | FR-021 | Navigation & Settings | System/Light/Dark appearance | Functional | Medium | - | 1. Select each mode. 2. Change OS theme in System mode. | - | Theme applied; System follows OS. | New | Not Run
TC-SET-002 | UC-37 | FR-021 | Navigation & Settings | Accessibility toggles persist | Functional | Medium | - | 1. Enable Larger text, High contrast, Reduce motion. 2. Reload. | - | Preferences persist and apply. | New | Not Run
TC-SET-003 | UC-37 | FR-021 | Navigation & Settings | Switch visibility in dark mode | UI | Low | Dark mode | 1. Open Settings. | - | Switch thumbs clearly visible; contrast >= 3:1. | New | Not Run
TC-SET-004 | UC-37 | FR-021 | Navigation & Settings | Admin settings page | Functional | Low | Admin | 1. Open /admin/settings. 2. Change theme. | - | Same preferences available in admin layout and applied. | New | Not Run
TC-LEGAL-001 | UC-46 | NFR-LEGAL | Navigation & Settings | Legal pages load | Functional | Low | - | 1. Open each /legal/:documentId from footer. 2. Open unknown id. | - | Content loads; unknown id shows not-found. | New | Not Run
TC-SAVE-001 | UC-38 | FR-017 | Saved Searches (Retired) | Save filters | Functional | Low | - | Retired | - | Retired with Saved Searches removal. | Retired | Retired |  |  |  | Replaced by TC-NAV-004.
TC-SAVE-002 | UC-38 | FR-017 | Saved Searches (Retired) | Alert on new match | Functional | Low | - | Retired | - | Retired; never implemented. | Retired | Retired |  |  |  | Remove FR-017 from active scope.
TC-BANK-001 | UC-30 | FR-014 | Bank Catalog & Loan | Scraper upserts with lastSeen | Integration | Medium | Live Metrobank | 1. Run scraper. 2. Open catalog. | - | metrobank_<ref> docs with lastSeen; 'Last verified' shown. | Existing (QA doc) | Passed (Dev) |  |  |  | Metrobank only (only active source).
TC-BANK-002 | UC-30 | FR-014 | Bank Catalog & Loan | Missing records delisted | Integration | Medium | Existing active record | 1. Run when record absent. | - | status delisted; lastSeen updated. | Existing (QA doc) | Passed (Dev)
TC-BANK-003 | UC-41 | FR-014 | Bank Catalog & Loan | Client write to bankProperties | Security | Medium | Normal user | 1. Direct write. | - | Denied. | Existing (QA doc) | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules. Previous note: BUG-008.
TC-BANK-004 | UC-30 | FR-014 | Bank Catalog & Loan | No duplicates on re-run | Integration | Medium | - | 1. Run scraper twice. | - | Same doc count; deterministic IDs. | New | Not Run
TC-BANK-005 | UC-31 | FR-014 | Bank Catalog & Loan | Catalog filters | Functional | Medium | Populated catalog | 1. Filter bank/city/price. | - | Correct results; empty state. | New | Not Run
TC-BANK-006 | UC-31 | FR-014 | Bank Catalog & Loan | Image fallback | UI | Low | Property without image | 1. Open catalog. | - | Fallback image, no broken icon. | New | Not Run |  |  |  | TODO cleanup 2026-09-30.
TC-BANK-007 | UC-33 | FR-016 | Bank Catalog & Loan | Admin bank-catalog job view | UI | Low | Admin | 1. Open Bank Catalog Status. | - | Queued/finished job status and last run shown honestly; intended inset/padding. | New | Not Run
TC-LOAN-001 | UC-32 | FR-015 | Bank Catalog & Loan | Known amortization value | Unit | Medium | - | 1. 2,000,000; 20% down; 6%; 20 yrs. | - | ≈ PHP 11,462.90. | Existing (QA doc) | Passed (Dev)
TC-LOAN-002 | UC-32 | FR-015 | Bank Catalog & Loan | Invalid inputs | Negative | Medium | - | 1. 0% rate, negative price, empty term. | - | Validation; no NaN/Infinity. | Existing (QA doc) | Not Run
TC-LOAN-003 | UC-32 | FR-015 | Bank Catalog & Loan | Price pre-filled from property | Functional | Low | Bank property | 1. Open detail. | - | Price pre-filled. | New | Not Run
TC-LOAN-004 | UC-32 | FR-015 | Bank Catalog & Loan | 0% interest computes P/n | Unit | Medium | - | 1. 1,200,000, 0% down, 0%, 10 yrs. | - | PHP 10,000.00. | New | Not Run
TC-BANK-008 | UC-30 | FR-014 | Bank Catalog & Loan | Fail closed on zero valid records | Unit | High | Fake source returning empty/invalid data | 1. Run scraper against fake source. | - | Run fails; no records delisted. | New | Not Run |  |  |  | May already be covered in the 28 Python tests — link the test name if so.
TC-BANK-009 | UC-30 | FR-014 | Bank Catalog & Loan | Record validation | Unit | Medium | Fake records | 1. Parse records without reference, with price 0/1/NaN. | - | Invalid records dropped; valid kept. | New | Not Run
TC-BANK-010 | UC-31 | FR-014 | Bank Catalog & Loan | Only Metrobank exposed | UI | Medium | Catalog page | 1. Open bank filter. | - | Metrobank only; no Landbank/BDO options presented as live. | New | Not Run
TC-BANK-011 | UC-33 | FR-026 | Bank Catalog & Loan | Admin queues refresh job | Functional | Medium | Admin | 1. Queue a Metrobank refresh. | - | scraperJobs doc created; UI shows queued (not done). | New | Not Run
TC-BANK-012 | UC-47 | FR-026 | Bank Catalog & Loan | Worker processes queued job | Integration | Medium | Trusted worker running (test project) | 1. Queue job. 2. Wait ≤ 30 s. | - | Job status updated with result; lastSeen refreshed. | New | Not Run
TC-BANK-013 | UC-31 | FR-014 | Bank Catalog & Loan | Keyword search, sort and pagination | Functional | Medium | Populated catalog | 1. Search a city prefix. 2. Sort by price. 3. Next page. | - | Correct results/count; no duplicates across pages. | New | Not Run
TC-BANK-014 | UC-41 | FR-026 | Bank Catalog & Loan | Non-admin cannot create scraper jobs | Security | Medium | Regular user | 1. Direct create scraperJobs doc. | - | Denied. | New | Not Run
TC-LOAN-005 | UC-32 | FR-015 | Bank Catalog & Loan | Total interest and disclaimer | UI | Medium | Bank property | 1. Compute estimate. | - | Principal, monthly payment, total interest shown with "Estimate only — not a loan offer" text. | New | Not Run
TC-ADM-001 | UC-36 | FR-016 | Admin Access & Management | Suspend and reinstate | Functional | Medium | Admin | 1. Suspend user. 2. Reinstate. | Test user | Status toggles; suspended user blocked. | Existing (QA doc) | Passed (Dev)
TC-ADM-002 | UC-35 | FR-016 | Admin Access & Management | Dashboard counts | Functional | Medium | Admin | 1. Open Admin Dashboard. | Seeded | Pending listings + open disputes match Firestore. | New | Not Run
TC-ADM-003 | UC-34 | FR-019 | Admin Access & Management | Active admin accesses /admin | Functional | High | Active admin | 1. Open /admin and nested routes directly. | - | Loading status then admin UI renders. | New | Not Run |  |  |  | P0.
TC-ADM-004 | UC-34 | FR-019 | Admin Access & Management | Regular user blocked | Security | High | Regular user | 1. Open /admin/listings directly. | - | Redirected; no admin content flash. | New | Not Run
TC-ADM-005 | UC-34 | FR-019 | Admin Access & Management | Suspended admin blocked | Security | High | Admin with status suspended | 1. Open /admin. | - | Suspended screen. | New | Not Run
TC-ADM-006 | UC-34 | FR-019 | Admin Access & Management | Missing/unreadable profile fails closed | Security | High | Auth user without profile | 1. Open /admin. | - | Retryable verification message; no admin UI. | New | Not Run
TC-ADM-007 | UC-34 | FR-019 | Admin Access & Management | Non-admin Firestore admin reads | Security | High | Regular user | 1. Query pending listings / disputes directly. | - | Denied. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-ADM-008 | UC-34 | FR-019 | Admin Access & Management | Admin guard unit tests | Unit | High | - | 1. Run node --test. | - | 5 access-state policy tests pass. | New | Passed |  |  |  | Included in the 48 passing Node tests.
TC-ADM-009 | UC-36 | FR-016 | Admin Access & Management | Suspend requires confirmation | UI | Low | Admin | 1. Click Suspend. | - | Danger-styled button + confirm step. | New | Not Run |  |  |  | Design Guide B5.
TC-SEC-001 | UC-41 | FR-005 | Security (Firestore Rules) | Renter confirms another's booking | Security | High | Seeded booking | 1. Direct write status Confirmed. | - | Denied. | Existing (QA doc) | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules. Previous note: BUG-008.
TC-SEC-002 | UC-41 | FR-006 | Security (Firestore Rules) | Owner confirms overlapping booking | Security | High | Seeded overlap | 1. Direct write. | - | Denied/rejected. | Existing (QA doc) | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-SEC-003 | UC-41 | FR-009 | Security (Firestore Rules) | Non-admin resolves dispute; non-owner reads docs | Security | High | Seeded | 1. Resolve as non-admin. 2. Read private fields. | - | Both denied. | Existing (QA doc) | Not Run |  |  |  | Unblocked (rules deployed 2026-10-04). Note: Firestore read of private fields can pass while the Cloudinary file itself stays public — see TC-VER-008 / GAP-01.
TC-SEC-004 | UC-30 | NFR-SEC | Security (Firestore Rules) | Secret not printed in logs | Security | High | GitHub Actions | 1. Run workflow. 2. Inspect logs. | - | Secret masked; data + trustScores updated. | Existing (QA doc) | Not Run
TC-SEC-005 | UC-41 | NFR-SEC | Security (Firestore Rules) | Unmatched collection deny-all | Security | Medium | - | 1. Write to random collection. | - | Denied. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-SEC-006 | UC-41 | FR-010 | Security (Firestore Rules) | Client write to trustScores | Security | High | User | 1. Direct write own listing score. | - | Denied. | New | Not Run |  |  |  | Unblocked: rules deployed to trusthome-ph on 2026-10-04 (BUG-008 resolved). Run on emulator, then on live rules.
TC-SEC-007 | UC-41 | NFR-SEC | Security (Firestore Rules) | Rules compile and deploy | Deployment | Critical | Firebase CLI | 1. firebase deploy --only firestore:rules. | - | Deploys without errors. | New | Passed | Rules deployment reported successful for trusthome-ph. |  | 2026-10-04 | Re-deploy and re-run after every rules change; record commit SHA.
TC-HARD-001 | UC-42 | NFR-REL | Release & Non-functional | Lazy route fallback | Functional | Medium | Throttled | 1. Navigate on slow 3G. | - | Accessible loading fallback. | Existing (QA doc) | Not Run
TC-HARD-002 | UC-42 | NFR-REL | Release & Non-functional | Error boundary | Functional | Medium | Test build | 1. Trigger runtime error. | - | Error screen with Reload. | Existing (QA doc) | Not Run
TC-HARD-003 | UC-35 | FR-016 | Release & Non-functional | Admin retry after load error | Functional | Medium | Admin | 1. Block Firestore. 2. Open dashboard. 3. Retry. | - | Error + Retry; loads after. | Existing (QA doc) | Not Run |  |  |  | BUG-001 regression.
TC-AUTO-001 | - | All | Release & Non-functional | npm test (Node test runner) | Unit | High | dev | Run node --test. | - | All pass (48 tests in the previous fresh run). | Updated | Passed |  |  |  | Now 48/48 (was 33). Re-run after final edits on the release commit.
TC-AUTO-002 | - | All | Release & Non-functional | npm run lint | Static | High | dev | Run lint. | - | No errors. | Existing (QA doc) | Passed |  |  |  | Passed in previous fresh run; re-run on release commit.
TC-AUTO-003 | - | All | Release & Non-functional | npm run build | Build | High | dev | Run build. | - | Succeeds; no large-bundle warning. | Updated | Passed |  |  |  | Passed in previous fresh run; vendor chunk split resolved BUG-007. Re-run on release commit.
TC-AUTO-004 | - | All | Release & Non-functional | Python unittest | Unit | High | bank_scraper | Run unittest discover. | - | All pass (28 tests after v2 promotion into bank_scraper/). | Updated | Passed |  |  |  | Now 28/28 (was 14; old package had 23). +5 tests cover backup/restore and Cloudinary migration.
TC-AUTO-005 | UC-39 | NFR | Release & Non-functional | Seed demo data | Integration | Medium | Live project | Dry run then seed. | - | Synthetic data created; no real IDs/Auth users. | Existing (QA doc) | Passed |  |  |  | Re-run in smoke test.
TC-UI-001 | - | NFR-USE | Release & Non-functional | Cross-browser & viewport walkthrough | UAT | High | Deployed build | User pages at 390 px, admin at 1280 px in Chrome, Edge, Firefox, mobile. | - | Layouts intact; 44 px targets; focus visible; labeled statuses. | Existing (QA doc) | Not Run
TC-UI-002 | - | NFR-USE | Release & Non-functional | Accessibility checks | UAT | Medium | Deployed build | 1. Keyboard-only navigation. 2. Contrast audit (Lighthouse/axe). 3. Photo alt text. | - | WCAG AA contrast; status never color-only; alt text present. | New | Not Run |  |  |  | Design Guide B7.
TC-UI-003 | - | NFR-USE | Release & Non-functional | Button states and padding | UI | Low | - | 1. Hover/press/disable buttons. | - | States visible; consistent horizontal padding. | New | Not Run |  |  |  | Cleanup 2026-09-30.
TC-E2E-001 | - | All | Release & Non-functional | End-to-end renter–owner–admin smoke test | E2E | Critical | Deployed build + rules | 1. Owner lists. 2. Admin approves (check admin notification). 3. Renter books. 4. Owner approves. 5. Renter logs deposit ref (address handoff: see GAP-03). 6. Renter completes + rates. 7. Workflow recomputes. 8. Second booking disputed + resolved. | Test accounts | Every step succeeds; correct notifications; statuses consistent. | New | Not Run |  |  |  | Run on the DEPLOYED current build (hosting last deployed 2026-10-01; fixes branch not yet deployed).
TC-AUTO-006 | - | NFR-SEC | Release & Non-functional | Firestore rules emulator suite | Security | High | Firebase CLI + Java | firebase emulators:exec --only firestore -- "node --test scripts/firestore-rules-smoke.mjs" | - | All pass. | New | Passed (Dev) | 9/9 passed in the latest recorded run. |  |  | Grow toward the full matrix in TH-08 §6.
TC-DEP-001 | - | NFR-REL | Release & Non-functional | Hosting parity with release commit | Deployment | Critical | Release commit tagged | 1. npm run build. 2. firebase deploy --only hosting. 3. Hard reload; check build/version marker. | - | Live site serves the release commit (booking calendar, admin Download UI visible). | New | Not Run |  |  |  | GAP-04: last hosting deploy 2026-10-01; fixes branch not deployed.
TC-UI-004 | - | NFR-USE | Release & Non-functional | Status text contrast | Accessibility | Medium | Light theme | 1. Check Verified/Pending chip text contrast. | - | Status text ≥ 4.5:1 (use #15803D / #B45309 for text). | New | Not Run |  |  |  | TH-07 §3.2 correction.
TC-OPS-001 | UC-43 | NFR-OPS | Operations & Data | Backup writes JSONL and refuses overwrite | Functional | High | Test project or emulator | 1. Run backup_firestore.py. 2. Run again to same target. | - | Timestamped JSONL per collection; second run refuses to overwrite. | New | Passed (Dev) | Covered by Python tests with fakes (28 passing). |  |  | No live backup recorded yet — run on live before any migration.
TC-OPS-002 | UC-44 | NFR-OPS | Operations & Data | Restore dry run validates without writing | Functional | High | Backup available | 1. Run restore_firestore.py <dir>. | - | Validation report; zero writes. | New | Passed (Dev) | Covered by Python tests with fakes.
TC-OPS-003 | UC-44 | NFR-OPS | Operations & Data | Restore --apply rehearsal (non-production) | Integration | Medium | Emulator or separate project | 1. Restore with --apply. 2. Compare counts. | - | Counts match backup; absent docs not deleted. | New | Not Run |  |  |  | Never on production.
TC-OPS-004 | UC-45 | FR-028 | Operations & Data | Document migration dry run only | Functional | High | Backup verified | 1. Run migrate_verification_documents.py (no --apply). | - | Report of eligible assets; no changes. | New | Not Run |  |  |  | Do NOT --apply until secure delivery path deployed (GAP-01).
TC-OPS-005 | - | NFR-SEC | Operations & Data | Service account key not tracked | Security | Critical | Repository | 1. git ls-files ¦ grep -i serviceAccount. 2. git log -p -S "private_key". | - | No key in index or history; key rotation recorded if ever exposed. | New | Not Run |  |  |  | GAP-05: revocation of previously shared keys not verified.
TC-OPS-006 | UC-30 | NFR-SEC | Operations & Data | GitHub Actions controlled run | Integration | High | FIREBASE_SERVICE_ACCOUNT secret | 1. workflow_dispatch scrape.yml. 2. Inspect logs and Firestore. | - | Scrape -> expiry -> trust steps succeed; secret masked; key file removed. | New | Not Run

## Summary
Test Cases by Module and Status
Module | Total | Passed | Passed (Dev) | Failed | Blocked | Not Run | Retired | Executed | Pass Rate
Authentication | 10 | 0 | 3 | 0 | 0 | 7 | 0 | 3 | 100%
Listing Intake | 17 | 0 | 6 | 0 | 0 | 11 | 0 | 6 | 100%
Admin Listing Review | 9 | 0 | 1 | 3 | 0 | 5 | 0 | 4 | 25%
Search & Browse | 8 | 0 | 2 | 0 | 0 | 6 | 0 | 2 | 100%
Booking | 23 | 0 | 8 | 0 | 0 | 15 | 0 | 8 | 100%
Ratings & Completion | 8 | 0 | 2 | 0 | 0 | 6 | 0 | 2 | 100%
Disputes | 9 | 0 | 1 | 0 | 0 | 8 | 0 | 1 | 100%
Public Profile | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 100%
Trust & Fairness Score | 14 | 0 | 2 | 0 | 0 | 12 | 0 | 2 | 100%
Owner Dashboard & My Listings | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | -
Notifications | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | -
Listing Map & Privacy | 12 | 0 | 0 | 1 | 0 | 11 | 0 | 1 | 0%
Navigation & Settings | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | -
Saved Searches (Retired) | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | -
Bank Catalog & Loan | 19 | 0 | 3 | 0 | 0 | 16 | 0 | 3 | 100%
Admin Access & Management | 9 | 1 | 1 | 0 | 0 | 7 | 0 | 2 | 100%
Security (Firestore Rules) | 7 | 1 | 0 | 0 | 0 | 6 | 0 | 1 | 100%
Release & Non-functional | 15 | 5 | 1 | 0 | 0 | 9 | 0 | 6 | 100%
Operations & Data | 6 | 0 | 2 | 0 | 0 | 4 | 0 | 2 | 100%
TOTAL | 199 | 7 | 33 | 4 | 0 | 153 | 2 | 44 | 90.91%
By Origin
Existing (QA doc) | 50
Updated | 8
New | 139
Retired | 2
Use cases | 47
Known gaps (open) | 11
Pass Rate = (Passed + Passed (Dev)) / Executed; Executed = Passed + Passed (Dev) + Failed. "Passed (Dev)" = dev/emulator/unit evidence only; re-run on the deployed build to promote to "Passed".

## Requirements
FR ID | Requirement | Priority | Source | Acceptance / Linked Tests
FR-002 (revise) | The system shall require a non-empty description of at most 400 words; 150 words is shown as a recommendation. | HIGH | Progress Report P1 Description | Empty/whitespace rejected; <150 words accepted; >400 rejected.
FR-008 (revise) | Only the renter manually marks a booking Completed; the scheduled job completes expired Confirmed bookings. | MEDIUM | Progress Report P1 Completion | Owner has no completion button; one Completed transition.
FR-009 (revise) | Submitting a dispute sets the booking to Disputed and records its prior status; Dismissed restores it; Founded keeps Disputed. | HIGH | Progress Report P1 Dispute | Booking and dispute states stay consistent; duplicate open disputes blocked.
FR-017 (retire) | Saved Searches removed; /saved-searches redirects to Browse without deleting records. | LOW | Cleanup 2026-09-30 | Redirect works; data preserved.
FR-019 | Only profiles with role admin and status active can render admin routes; missing/unreadable profiles fail closed with retry. | HIGH | Progress Report P0 Admin login | TC-ADM-003 to 008.
FR-020 | Admin broadcast notifications (__admins__) are limited to new listing submissions and disputes; booking requests notify only the listing owner; feeds are isolated by rules. | HIGH | Progress Report P0 Notifications | TC-NOTIF-005 to 009, TC-NOTIF-012.
FR-021 | One My Activity page (Listings, Bookings, Requests tabs) and Settings with System/Light/Dark plus persisted accessibility preferences. | LOW | Progress Report P2 Navigation | TC-NAV-001 to 004, TC-SET-001 to 003.
FR-022 | Optional approximate map pin stored as a 5-char geohash; exact address kept in listingPrivate readable by owner/admin only. | MEDIUM | Progress Report P2 Map | TC-MAP-001 to 008, 011, 012.
FR-023 | My Listings shows photo, city, type, bedrooms, price, status, review note and per-listing pending-request counts. | MEDIUM | Progress Report P1 Owner visibility | TC-MYL-001 to 006.
FR-024 | The renter sees the exact property address only after the booking is Confirmed. | HIGH | TH-03 §3.4, §4.6 | TC-MAP-009, 010. KNOWN GAP GAP-03 — current client approval does not copy the address.
FR-005 (revise) | The listing owner approves a Pending request through a transaction that rechecks the request is still Pending and owned by them; only Pending -> Confirmed is permitted for owners. Overlap with Confirmed bookings must be rejected, including under concurrent approvals. | HIGH | Progress Report 2026-10-04 §3 | TC-BOOK-003, 019, 021, 022, 023.
FR-025 | Listings have a purpose (rent or sale). Only verified rent listings are bookable; sale listings are excluded from rental fairness/trust comparisons. | HIGH | Progress Report 2026-10-04 §3, §4 | TC-BOOK-020, TC-SRCH-008, TC-FAIR-007, TC-INTAKE-015.
FR-026 | Admins can queue bank-catalog refresh jobs (scraperJobs) that a trusted worker processes; job state is shown honestly. | MEDIUM | Progress Report 2026-10-04 §5 | TC-BANK-011, 012, 014.
FR-027 (NFR-OPS) | Trusted tooling can back up all top-level collections to JSONL and validate/dry-run restores before any write. | MEDIUM | Progress Report 2026-10-04 V2 tools | TC-OPS-001 to 003.
FR-028 (roadmap) | Verification documents are delivered only to the owner/admin through short-lived authenticated URLs; never publicly fetchable. | HIGH | Progress Report 2026-10-04 P0 | TC-VER-008, TC-OPS-004. GAP-01.

## Known Gaps
Gap ID | Title | Severity | Description (as of 2026-10-04) | Owner | Status | Linked tests / FR | Exit criteria | Reference
GAP-01 | Verification-document delivery and privacy | P0 | Cloudinary blocks PDF delivery (show_original_customer_untrusted); unsigned-preset URLs are public if known. Admin Download cannot bypass the block. | Carillo + Andresa | Open | TC-VER-004, 008, 009; FR-028 | Admins can view documents; no ID document fetchable without authorization; Cloudinary ticket outcome recorded. | TH-04 §5–6
GAP-02 | Booking overlap race | P0 | Overlap query runs before the transaction; simultaneous approvals can both confirm. | Laurente | Open | TC-BOOK-019; FR-005, FR-006 | Option A or B implemented and concurrent test passes, or claim formally narrowed. | TH-03 §4.6
GAP-03 | Exact address not handed to confirmed renter | P0 | Client approval does not copy listingPrivate.address to the booking; callable path not deployed. | Laurente + Carillo | Open | TC-MAP-009, 010; FR-024 | Renter sees address only after confirmation, or UI copy changed. | TH-03 §3.4
GAP-04 | Hosting not deployed for current branch | P1 | Last hosting deploy 2026-10-01; PR #42 fixes branch not merged to dev or deployed. | Andresa | Open | TC-DEP-001, TC-E2E-001 | Merged, tagged commit deployed; smoke test passed. | TH-05 §7–8
GAP-05 | Admin SDK key revocation unverified | P1 | Local serviceAccountKey.json is git-ignored; whether any previously shared key was revoked is unknown. | Solpico | Open | TC-OPS-005 | Key rotated if ever exposed; history scanned; secret updated. | TH-04 §7
GAP-06 | Cloud Functions not deployed | P1 | Callable confirmation and scheduled jobs exist in source only (Blaze/Cloud Build). | Team decision | Open | TC-JOB-001, TC-BOOK-019 | Either deployed with budget alert, or source clearly marked inactive. | TH-04 §8
GAP-07 | 'Use my exact address' button not rendering | P2 | Open defect from release QA (#11–12). | Carillo | Open | TC-MAP-003 | Button renders after hard reload on deployed build. | TH-03 §3.4
GAP-08 | Landbank unverified; BDO placeholder | P2 | Metrobank is the only active source. | Solpico | Open | TC-BANK-010 | Parser validated with fixtures + dry run before enabling. | TH-06 §2
GAP-09 | Dispute window on Completed bookings undecided | P2 | Policy pending approval. | Laurente | Open | TC-DISP-009 | Policy recorded in TH-03 §6 and enforced in rules. | TH-03 §6
GAP-10 | Weekly maintenance cadence | P2 | Expired bookings and trust scores may lag up to a week. | Solpico | Open | TC-JOB-003 | Cadence decision documented. | TH-06 §3
GAP-11 | No live backup/restore rehearsal | P1 | Tools tested with fakes only. | Solpico | Open | TC-OPS-001, 003 | Verified live backup + non-production restore rehearsal recorded. | TH-06 §4
BUG-008 | Latest firestore.rules not deployed | P0 | Previously blocked many security tests. | Andresa | Resolved | TC-SEC-007 | Rules deployed to trusthome-ph on 2026-10-04. | TH-04 §3.3