## Read Me
TrustHome PH — Use Cases & Test Cases Catalog (Rev 2, 2026-10-01)
Built from the Rev 2 document set (01–07 PDFs) and the Current Progress Report (Oct 1, 2026). Earlier sources (Build Instructions, System Build Plan, Firebase Setup Plan, Design Guide, Versioning Plan) are superseded; see the mapping below.
Sheets
Use Cases — 48 use cases (UC-43 to UC-48 added in Rev 2).
Test Cases — 202 test cases. IDs from the QA doc are kept; new ones continue each prefix. Rev 2 adds TC-PURP, TC-API, TC-DOC, TC-OPS and TC-NOTIF-012 to 015.
Summary — live counts by module, status and origin (formulas; update automatically). "Unassigned module check" must be 0.
Proposed FRs — FR-019 to FR-029 and NFR-COST-01, NFR-SEC-02, NFR-REL-02 for the QA doc.
What changed in Rev 2 (Oct 1)
1. Rules were deployed on Oct 1 (commit a1fe48e), so 23 cases that waited on "BUG-008 / rules deploy" moved from Blocked to Not Run. Run them now.
2. Cases that need live booking confirmation stay Blocked by F-05 until the trusted API (v1.4) is deployed: TC-SEC-002, TC-NOTIF-002.
3. Cases that need private documents stay Blocked by F-16 until v1.4: TC-VER-006, document part of TC-SEC-003.
4. TC-MAP-003 changed Failed -> Passed (Sep 30 live test). TC-SEC-007 changed Not Run -> Passed (rules deployed).
5. Automated counts updated: 47 Node tests, 23 Python tests, npm audit 0 vulnerabilities (TC-AUTO-001, 004, 006).
6. UC-15 and UC-10 now describe the trusted API (confirmation, document preview).
Origin column
Existing (QA doc): unchanged from TrustHomePH_QA_Documentation_Updated.docx.
Updated: exists in the QA doc but its expected result or data changed (see Remarks).
New: not yet in the QA doc. Retired: feature removed (Saved Searches); kept for traceability.
Status meanings (use exactly these)
Passed — executed on the deployed test project with evidence (screenshot or log) and a tester name.
Passed (Dev) — passed only locally / on emulator / by unit test. Must be re-run live before release.
Failed — executed and the actual result differs. Log a defect (F-xx) and put its ID in Remarks.
Blocked — cannot run yet; Remarks must name the blocker (F-05, F-16, ...). Not Run — runnable but not yet run.
How to use
Edit only the yellow columns in Test Cases: Status, Actual Result, Tester, Date. Status uses a dropdown.
Example: Status = Passed · Actual Result = 'Booking Confirmed; renter bell shows 1' · Tester = Laurente · Date = 2026-10-06.
Execution order for the next two weeks is in 07 QA & Testing Strategy §6.
Old source name -> Rev 2 document
Build Instructions -> 01 Product Requirements & Scope
System Build Plan -> 02 System Architecture & Data Design
Firebase Setup Plan -> 03 Infrastructure, Setup & Deployment (secrets/rules parts -> 04 Security & Privacy)
Design Guide -> 05 UI/UX Design System
Versioning Plan -> 06 Roadmap & Release Plan
QA Documentation (test approach) -> 07 QA & Testing Strategy

## Use Cases
UC ID | Use Case | Module | Primary Actor | Related FR | Preconditions | Main Flow | Alternate / Exception Flows | Postconditions | Source | Version
UC-01 | Register an account | Authentication | Guest | FR-001 | Visitor is signed out. | 1. Open Login / Register. 2. Enter name, email, password. 3. Submit. 4. System creates Firebase Auth account and users/{uid} profile (role user, status active). 5. Redirect to home/dashboard. | A1. Email already in use -> inline error. A2. Weak/short password -> inline error. A3. Network failure -> error message, no partial profile. | User is signed in with an active user profile. | Build Instructions §2.3, §6; Firebase Setup §4 | v0.1
UC-02 | Log in with email and password | Authentication | User / Admin | FR-001 | Account exists. | 1. Open Login. 2. Enter email + password. 3. System authenticates and loads profile. 4. Redirect to the user's landing page. | A1. Wrong password / unknown email -> inline error, no session. A2. Suspended account -> suspended-account screen; protected actions blocked. | Session active; nav shows account menu + bell. | Build Instructions §6 | v0.1
UC-03 | Sign in with Google | Authentication | Guest / User | FR-001 | Google sign-in enabled in Firebase. | 1. Click Continue with Google. 2. Choose account. 3. On first sign-in, system creates users profile. 4. Redirect. | A1. User closes popup -> stays on login, no error loop. A2. Existing email/password account with same email -> handled without duplicate profile. | Signed in; single profile per UID. | Firebase Setup §4 | v0.1
UC-04 | Log out | Authentication | User / Admin | FR-001 | User is signed in. | 1. Open account menu. 2. Click Log out. 3. Session cleared; redirected to public page. | A1. Using back button after logout does not reveal protected pages. | Signed out. | Design Guide p.10 | v0.1
UC-05 | Manage profile / account | Account | User | FR-001 | Signed in. | 1. Open profile/account page. 2. Edit allowed fields (e.g., name). 3. Save. | A1. User cannot change own role or status (rules deny). | Profile updated; role/status unchanged. | Progress Report v0.1 | v0.1
UC-06 | Create a listing and submit for review | Listing Intake | User (Owner) | FR-002, FR-003 | Signed in, active account. | 1. Open Create Listing (multi-step). 2. Enter type, address/area, city, bedrooms, bathrooms, size, rent, availability date, amenities, description. 3. Upload >= 4 photos to Cloudinary. 4. Upload one ownership document + one government photo ID. 5. Add >= 1 showing window (day + start/end time). 6. Optionally place an approximate map pin. 7. Submit -> verificationStatus = pending. | A1. Missing required field -> field-level error, submission blocked. A2. Description empty/whitespace or > 400 words -> blocked (150 words is a recommendation only). A3. < 4 photos -> blocked. A4. Missing either document -> blocked. A5. No valid showing window / end before start -> blocked. A6. Upload fails -> error, user can retry. | Pending listing (not public); exact address stored in listingPrivate/{id}; public doc has no address field. | Build Instructions §2.1–2.3; Progress Report v1.1, P1 | v0.1 / v1.1
UC-07 | Edit a listing / resubmit after changes requested | Listing Intake | User (Owner) | FR-002, FR-003 | Owner has an existing listing. | 1. Open My Listings -> Edit. 2. Change fields/photos/documents/showing windows. 3. Save / resubmit. 4. If status was changes-requested, listing returns to pending. | A1. Edit breaks any intake rule -> same errors as creation (edit parity). A2. Non-owner opens edit URL -> denied. | Listing updated; resubmitted listing back in admin queue. | Progress Report v1.1 | v1.1
UC-08 | Set location with approximate map pin | Listing Map & Privacy | User (Owner) | FR-022 | Owner on create/edit listing. | 1. Type a location in map search. 2. Geocoder (with PH-specific retry) returns a pin. 3. Or click 'Use my exact address' to geocode the private address. 4. Adjust pin; save. 5. Public doc stores only a 5-char geohash marked approximate. | A1. Address not found -> message; owner can place pin manually. A2. Invalid coordinates -> rejected. A3. Pin optional -> listing saves without map. A4. OPEN BUG: 'Use my exact address' button not rendering in live browser. | Public listing has coarse location only; exact lat/long never public. | Progress Report P2 Map; cleanup 2026-09-30 | v1.3+
UC-09 | View My Listings | Owner Listing Visibility | User (Owner) | FR-023 | Signed in; owns >= 0 listings. | 1. Open My Activity -> My Listings. 2. See card per listing: photo, city, type, bedrooms, price, verification status, review note, pending-request count. 3. View / Edit actions. 4. Tap request count -> Booking Requests tab filtered to that listing. | A1. No listings -> empty state with Create Listing CTA. A2. Request count fails to load -> 'unavailable' state (not zero). | Owner sees status of every listing; exact address/documents not shown. | Progress Report P1 Owner visibility | v1.3+
UC-10 | Review a pending listing | Admin Listing Review | Admin | FR-003 | Admin signed in; pending listing exists. | 1. Open Listing Review Queue. 2. View photos; ownership document and government ID load through short-lived URLs from GET /api/listings/{id}/documents/{kind}. 3. Check name match + document validity (plausibility only). 4. Choose Approve, Request changes (with note), or Reject (with note). 5. Owner is notified. | A1. Document PDF fails to render -> link still openable. A2. Queue load fails -> error + Retry. | Approved -> verified + verifiedAt, public with 'Verified – document reviewed' badge. Changes requested -> owner sees note. Rejected -> permanent. | Build Instructions §2.2, §2.3; Build Plan §3 | v0.1 / v1.1
UC-11 | Browse and filter verified listings | Search & Browse | Guest / User | FR-004 | Verified listings exist. | 1. Open Browse. 2. Apply city, price range, type filters. 3. Results sorted by Trust & Fairness Score by default. 4. Change sort. | A1. No matches -> empty state. A2. Pending/rejected/suspended listings never shown. | Filtered verified list displayed. | Build Instructions §3.1; Design Guide p.2 | v0.1
UC-12 | View listing details | Search & Browse | Guest / User | FR-004, FR-010, FR-022 | Listing is verified. | 1. Open a listing card. 2. See photos, Verified badge, price, trust score + cue, price-fairness label, availability/showing windows, reviews, approximate map, Request Booking CTA. | A1. No pin -> map hidden. A2. Guest clicks Request Booking -> prompted to sign in. A3. Pending listing URL opened by non-owner -> not found/denied. | Details displayed; no exact address or documents visible. | Design Guide p.3; Progress Report v1.3 | v0.1 / v1.3
UC-13 | View a public profile | Public Profile | Guest / User | FR-018 | Target user exists. | 1. Open owner's profile from listing. 2. See trust score, rating, Verified badge, founded-dispute flag (if count > 0). | A1. No founded disputes -> no warning. | Profile displayed; flag computed from Founded disputes. | Design Guide p.11; Build Plan §6 | v0.3
UC-14 | Request a booking / viewing | Booking | User (Renter) | FR-005, FR-006 | Signed in; listing verified; not the renter's own listing. | 1. On Listing Detail click Request Booking. 2. Select start/end date (within showing windows). 3. System checks overlap against Confirmed bookings only. 4. Create booking status Pending. 5. Owner notified. | A1. Overlap with Confirmed -> 'dates unavailable', no doc. A2. End before start / past date -> blocked. A3. Dates not selected -> button disabled with reason. A4. Pending overlaps are allowed (competing requests). A5. Suspended user -> blocked. | Pending booking exists; owner has a notification. | Build Instructions §3.1, §4; Build Plan §4 | v0.2
UC-15 | Confirm a booking request | Booking | User (Owner) | FR-005, FR-006 | Pending request on owner's listing. | 1. Open My Activity -> Booking Requests. 2. Click Confirm. 3. Client sends POST /api/bookings/{id}/confirm with the user's Firebase ID token. 4. API verifies token, owner, active status, and re-checks overlap inside a Firestore transaction holding the per-listing lock. 5. Status -> Confirmed; renter notified; exact-address handoff created. | A1. Overlaps an existing Confirmed booking -> 409, request stays Pending (first confirmation wins). A2. Non-owner / suspended / signed-out -> 403/401. A3. API unreachable -> 'service unavailable' message; UI never falls back to a direct Firestore write. A4. Direct client write of status Confirmed -> denied by Firestore rules. | Booking Confirmed; range blocks future overlaps. | Requirements §7; Architecture §6–7 (supersedes Build Plan §4) | v0.2 / v1.4
UC-16 | Decline a pending request | Booking | User (Owner) | FR-005 | Pending request on owner's listing. | 1. Open Booking Requests. 2. Click Decline. 3. Pending booking document deleted (no 'Cancelled' status). | A1. Attempt to decline a Confirmed booking -> not allowed. | Request removed. | Progress Report v1.2 | v1.2
UC-17 | Log deposit transaction reference | Deposit Accountability | User (Renter) | FR-007 | Renter's booking is Confirmed; deposit paid off-platform (GCash/bank). | 1. Open My Bookings -> booking. 2. Enter transaction reference. 3. Save; reference visible to renter and owner. | A1. Booking Pending -> field unavailable. A2. Empty reference -> validation error. A3. Owner or third party tries to write it -> denied. | depositReference stored on booking. | Build Instructions §3.2 | v1.2
UC-18 | Mark a booking completed | Booking Completion | User (Renter) | FR-008 | Renter's booking is Confirmed. | 1. Open My Bookings. 2. Click Mark completed (renter is the single manual authority). 3. Status -> Completed; rating prompt shown. | A1. Owner side has no Mark completed button. A2. Pending booking cannot be completed. | Booking Completed; counts toward trust score. | Progress Report P1 duplicate completion | v1.2 / v1.3+
UC-19 | Auto-complete expired bookings | Scheduled Jobs | System (GitHub Actions) | FR-008 | Confirmed bookings with endDate < today. | 1. Workflow runs complete_expired_bookings.py. 2. Matching bookings -> Completed. 3. Trust-score recomputation runs next. | A1. Non-expired or non-Confirmed bookings untouched. A2. Workflow failure -> visible in Actions history; manual re-run. | Expired bookings Completed. | Build Plan §4; Progress Report v0.2 | v0.2
UC-20 | View exact address after confirmation | Listing Map & Privacy | User (Renter) | FR-024 | Renter has a Confirmed booking. | 1. Open the confirmed booking. 2. Exact property address is shown (handoff from listingPrivate). | A1. Pending/declined booking -> address hidden. A2. Unrelated user -> denied. | Renter sees exact address only after confirmation. | Build Instructions §2.1; cleanup 2026-09-30 | v1.3+
UC-21 | View My Activity | Navigation & Settings | User | FR-021 | Signed in. | 1. Open account menu -> My Activity. 2. Switch tabs: My Listings, My Bookings, Booking Requests (tab reflected in URL). | A1. Old direct routes still work. A2. New user -> empty states in each tab. | One entry point for all activity. | Progress Report P2 Navigation | v1.3+
UC-22 | Rate and review a completed booking | Ratings & Reviews | User (Renter / Owner) | FR-008 | Booking is Completed. | 1. Open rating prompt. 2. Select 1–5 score, optional comment. 3. Submit; review shows on listing. | A1. Booking not Completed -> denied. A2. Duplicate rating by same rater -> blocked. A3. Score outside 1–5 -> rejected. | Rating stored; trust score updated on next run. | Build Instructions §4; Build Plan §2 | v0.2
UC-23 | Raise a dispute | Disputes | User (Renter) | FR-009 | Renter's booking is Confirmed (or Completed, per agreed window). | 1. Open booking -> Raise Dispute. 2. Enter reason + evidence description. 3. Submit: dispute Open; booking prior status recorded; booking -> Disputed; dispute id linked. 4. Admins notified. | A1. Duplicate open dispute on same booking -> blocked. A2. Pending booking -> not allowed. A3. Empty reason -> validation. | Open dispute in admin queue; booking Disputed. | Build Instructions §3.3; Progress Report P1 Dispute | v0.3 / v1.3+
UC-24 | Resolve a dispute | Disputes | Admin | FR-009 | Open dispute exists. | 1. Open Dispute Review Queue. 2. Review booking, reporter, reason, deposit reference. 3. Mark Founded or Dismissed with notes. 4. Reporter notified. | A1. Founded -> owner account + listing suspended, booking stays Disputed, public accountability count +1. A2. Dismissed -> booking restored to prior status, no flag. A3. Non-admin attempts -> denied. | Dispute closed with decision-maker, notes and resolvedAt. | Build Instructions §3.3; Build Plan §6 | v0.3 / v1.3+
UC-25 | Recompute trust scores | Trust & Fairness Score | System (GitHub Actions) | FR-010 | Verified listings, bookings, ratings exist. | 1. Workflow runs trust-score recomputation. 2. For each verified listing: booking score (recency-weighted Completed only), rating score, fairness score. 3. Write trustScores/{listingId} with label + computedAt. | A1. No ratings -> no divide-by-zero. A2. No comparables -> 'Insufficient data'. | trustScores refreshed; Browse ordered by score. | Build Plan §5 | v0.1–v1.3
UC-26 | Flag repeated self-booking pattern | Anti-Gaming | System / Admin | FR-011 | Same renter–owner pair has completed bookings. | 1. Recompute detects >= 3 completed bookings for same pair within 30 days. 2. Set manualReviewRequired = true, selfBookingPatternCount. 3. Admin reviews. | A1. Only 2 in 30 days, or 3 spread over > 30 days -> no flag. | Suspicious listing flagged for manual review. | Build Instructions §5; Progress Report v1.3 | v1.3
UC-27 | View owner dashboard | Owner Dashboard | User (Owner) | FR-012 | Signed in. | 1. Open My Dashboard. 2. See listings, inquiries, pending requests, confirmed bookings, completed stays. | A1. New user -> zeros/empty state with CTA. | Counts match Firestore. | Build Instructions §6 (#10); Design Guide p.12 | v1.3
UC-28 | View and manage notifications | Notifications | User | FR-013, FR-020 | Signed in. | 1. Bell shows unread count. 2. Open /notifications. 3. Mark one / all read. | A1. No notifications -> empty state. A2. Cannot read other users' notifications. A3. Notification write failure does not fail the main action. | Unread count accurate. | Progress Report v1.3 Notifications | v1.3
UC-29 | View admin dispute notifications | Notifications | Admin | FR-013, FR-020 | Admin signed in. | 1. Admin bell inside /admin/* shows dispute notifications only. 2. Open admin inbox; mark read (shared read state). | A1. Booking-request notices never appear for admins. A2. Regular users cannot read __admins__ feed. | Admin feed contains disputes only. | Progress Report P0 Notification split | v1.3+
UC-30 | Scrape Metrobank catalog | Bank Catalog | System (GitHub Actions) | FR-014 | FIREBASE_SERVICE_ACCOUNT secret set. | 1. Workflow writes key file from secret. 2. Scraper fetches Metrobank pages. 3. Upserts bankProperties/metrobank_<ref> with merge, status active, lastSeen. 4. Missing previously-active records -> delisted. | A1. Layout change breaks scraper -> job fails, marketplace unaffected. A2. Secret never printed in logs. | Catalog current with lastSeen. | Build Plan §7; Firebase Setup §10 | v0.1
UC-31 | Browse bank-acquired catalog | Bank Catalog | Guest / User | FR-014 | bankProperties populated. | 1. Open Bank Catalog. 2. Filter by bank, city, price. 3. Each card shows 'Last verified: <date>'. | A1. Missing image -> fallback image. A2. No matches -> empty state. A3. Delisted properties hidden/marked. | Read-only catalog displayed. | Build Plan §7; Design Guide p.7 | v0.1
UC-32 | Estimate loan amortization | Loan Calculator | Guest / User | FR-015 | On a bank property detail page. | 1. Price pre-filled. 2. Enter down payment %, annual rate, term years. 3. Monthly payment computed client-side. | A1. 0% rate -> P/n (no NaN). A2. Negative/empty inputs -> validation. A3. Down payment >= 100% -> validation or zero. | Estimate displayed. | Build Plan §8 | v0.3
UC-33 | Monitor bank catalog status | Admin Bank Catalog | Admin | FR-014, FR-016 | Admin signed in. | 1. Open Bank Catalog Status / scrape log. 2. See last run per bank. 3. Trigger/re-run workflow (via GitHub Actions). | A1. Stale lastSeen reveals failed runs. | Admin knows catalog freshness. | Design Guide p.20 | v0.1
UC-34 | Access the admin panel | Admin Access | Admin | FR-019 | Account exists. | 1. Navigate to /admin or a nested admin route. 2. Guard waits with visible status while profile loads. 3. Only role admin + status active renders admin routes. | A1. Regular user -> redirected. A2. Suspended -> suspended screen. A3. Missing/unreadable/incomplete profile -> fail closed with retry message. A4. Signed out -> login. | Only verified active admins see admin UI. | Progress Report P0 Admin login | v1.3+
UC-35 | View admin dashboard | Admin Dashboard | Admin | FR-016 | Admin signed in. | 1. Open Admin Dashboard. 2. See pending-listing count, open-dispute count, recent activity. | A1. Load error -> message + Retry. | Counts match Firestore. | Design Guide p.16; Progress Report v1.0 | v0.2 / v1.0
UC-36 | Suspend or reinstate a user | User Management | Admin | FR-016 | Admin signed in. | 1. Open User Management. 2. Suspend account (danger button, confirm). 3. Later reinstate. | A1. Suspended user cannot list, book, rate, or dispute. A2. Admin cannot suspend self (recommended check). | User status toggled. | Design Guide p.19 | v0.2
UC-37 | Change appearance and accessibility settings | Navigation & Settings | User | FR-021 | Any user (signed in). | 1. Open Settings. 2. Choose System/Light/Dark. 3. Toggle Larger text, High contrast, Reduce motion. 4. Reload -> preferences persist. | A1. System mode follows OS preference changes. A2. Switch thumbs visible in dark mode. | Preferences applied and persisted. | Progress Report P2 Settings; Design Guide B7 | v1.3+
UC-38 | Open retired Saved Searches URL | Saved Searches (Retired) | User | FR-017 (retired) | Legacy link or bookmark. | 1. Open /saved-searches. 2. Redirected to Browse. 3. Existing savedSearches records are not deleted. | A1. Menu no longer shows Saved Searches. | Safe redirect; data preserved. | Progress Report cleanup 2026-09-30 | v1.3+
UC-39 | Seed synthetic demo data | Operations | Developer | NFR | Firebase Admin credentials available. | 1. Run seed_demo_data.py --dry-run. 2. Review counts. 3. Run seed_demo_data.py. | A1. No real IDs, passwords or Auth users created. A2. Placeholder documents labeled synthetic. | Demo dataset present. | Progress Report v0.3 validation | v0.3
UC-40 | Migrate legacy listing addresses | Operations | Developer / Admin | FR-022 | Firestore backed up; maintenance window. | 1. Run migrate_listing_addresses.py (dry run default). 2. Inspect counts + conflicts. 3. Run with --apply. 4. Deploy rules and frontend. | A1. Re-run is idempotent. A2. Existing private addresses preserved. A3. Conflicting-owner records reported, not overwritten. | Public listings have no address field; addresses in listingPrivate. | Progress Report P2 Map | v1.3+
UC-41 | Enforce data-access rules | Security (Firestore Rules) | System | NFR-SEC | Latest firestore.rules deployed. | 1. Every client read/write is evaluated by rules. 2. Deny-all fallback for unmatched paths. | A1. Direct SDK writes bypassing UI are denied when forbidden. | Data protected even against malicious clients. | Firebase Setup §11; Progress Report backend readiness | v0.1–v1.3
UC-42 | Recover from loading and runtime errors | Release Hardening | User / Admin | FR-016, NFR-REL | App running. | 1. Lazy routes show accessible loading fallback. 2. Runtime error -> top-level error screen with Reload. | A1. Slow network -> fallback, not blank page. | No blank screens. | Progress Report v1.0 | v1.0
UC-43 | Choose listing purpose and price period | Listing Purpose | User (Owner) | FR-025 | Signed in; creating or editing a listing. | 1. Choose For rent or For sale. 2. For rent: choose Short-term (nightly) or Long-term (monthly). 3. Enter the price for that period (or one-time asking price for sale). 4. Submit. | A1. No purpose chosen -> blocked. A2. Sale listing -> booking controls hidden; booking request rejected by rules. | Purpose and pricePeriod stored; shown on Browse, Detail, Admin review and My Listings. | Progress Report Oct 1 follow-up | v1.3+
UC-44 | Receive admin alert for a new listing submission | Notifications | Admin | FR-026 | Admin signed in. | 1. Owner submits listing. 2. System writes the pending listing and a listing_submitted notification to __admins__ in one batch. 3. Admin opens bell -> alert links to the review item. | A1. Notification write rejected -> whole batch fails, owner sees error and can retry. | Admin sees one alert per submission. | Progress Report Oct 1 follow-up | v1.3+
UC-45 | Preview private verification documents | Private Documents | Admin / Owner | FR-028 | Listing has documents stored as Cloudinary authenticated assets. | 1. Admin opens review item (or owner opens own listing). 2. Client calls GET /api/listings/{id}/documents/{kind} with ID token. 3. API checks admin or owner, returns a signed download URL that expires (default 5 min). 4. Image/PDF preview renders. | A1. Other user -> 403. A2. URL reused after expiry -> Cloudinary rejects. A3. Legacy record -> falls back to migrated asset or shows "migration pending". | Document visible only to owner/admin for a short time; no permanent public URL exists. | Security & Privacy §5 | v1.4
UC-46 | Rotate the Firebase service-account key | Operations | Team lead | NFR-SEC-02 | Owner access to the Google Cloud project. | 1. Create a new key per consumer (GitHub Actions, API). 2. Update GitHub secret and Vercel env vars. 3. Re-run workflow and API health check. 4. Delete the old key. 5. Scan Git history for leaked keys. | A1. Workflow fails after rotation -> secret pasted wrongly; fix and re-run before deleting old key. | Old key cannot authenticate; history scan recorded. | Infrastructure §6; Progress Report F-01 | v1.4
UC-47 | Back up Firestore without Blaze | Operations | Team lead | NFR-REL-02 | Admin credentials in a trusted machine. | 1. Run the JSON backup script. 2. Verify document counts per collection. 3. Store the archive privately. | A1. Quota exceeded -> resume the next day; do not run migrations without a fresh backup. | Restorable JSON snapshot dated before any migration. | Infrastructure §8 | v1.4
UC-48 | Migrate verification documents to private delivery | Private Documents | Team lead | FR-028 | Backup taken; API deployed. | 1. Run migration in dry-run mode and review counts. 2. Apply: change each legacy asset to authenticated type, store publicId in listingPrivate, remove URL fields from listings. 3. Spot-check old URLs no longer load. | A1. Asset missing in Cloudinary -> report row for manual follow-up. | No verification document is reachable from a public URL. | Security & Privacy §5 | v1.4

## Test Cases
TC ID | UC ID | FR ID | Module | Title | Test Type | Priority | Preconditions | Test Steps | Test Data | Expected Result | Origin | Status | Actual Result | Tester | Date | Remarks
TC-AUTH-001 | UC-01 | FR-001 | Authentication | Register with valid email/password | Functional | High | Signed out | 1. Open Register. 2. Enter name, email, password. 3. Submit. | New email; password >= 6 chars | Account created; users/{uid} saved with role user, status active; redirected. | Existing (QA doc) | Passed (Dev) |  |  |  | Re-run on deployed build.
TC-AUTH-002 | UC-02 | FR-001 | Authentication | Login with wrong password | Negative | High | Registered account | 1. Open Login. 2. Enter registered email + wrong password. 3. Submit. | Registered test account | Inline error shown; no session created. | Existing (QA doc) | Passed (Dev)
TC-AUTH-003 | UC-03 | FR-001 | Authentication | Google sign-in creates profile on first login | Functional | High | Google sign-in enabled | 1. Click Continue with Google. 2. Pick account. | Google test account | Signed in; profile created on first sign-in only. | Existing (QA doc) | Passed (Dev)
TC-AUTH-004 | UC-01 | FR-001 | Authentication | Register with an email already in use | Negative | Medium | Account exists | 1. Register again with same email. | Existing email | Inline 'email already in use' error; no second profile. | New | Not Run
TC-AUTH-005 | UC-01 | FR-001 | Authentication | Register with weak password / invalid email | Negative | Medium | Signed out | 1. Enter 'abc' as password, or 'user@' as email. 2. Submit. | Invalid inputs | Inline field errors; submit blocked. | New | Not Run
TC-AUTH-006 | UC-02 | FR-001 | Authentication | Login with valid credentials | Functional | High | Registered account | 1. Enter valid email + password. 2. Submit. | Registered account | Signed in; account menu + bell visible; redirected. | New | Not Run |  |  |  | Mirrors acceptance criteria US-001.
TC-AUTH-007 | UC-02 | FR-016 | Authentication | Suspended account login | Negative | High | Account suspended by admin | 1. Log in as suspended user. 2. Try to create listing / book. | Suspended test user | Suspended-account screen/notice; protected actions blocked by UI and rules. | New | Not Run
TC-AUTH-008 | UC-04 | FR-001 | Authentication | Logout clears session | Functional | Medium | Signed in | 1. Log out. 2. Press browser Back. 3. Open /notifications directly. | Any user | Session cleared; protected pages redirect to login. | New | Not Run
TC-AUTH-009 | UC-03 | FR-001 | Authentication | Cancel Google popup | Negative | Low | Signed out | 1. Click Continue with Google. 2. Close popup. | - | Stays on login with no crash or infinite spinner. | New | Not Run
TC-AUTH-010 | UC-05 | FR-001 | Authentication | User cannot escalate own role/status | Security | High | Signed in as regular user | 1. Via SDK/console, update own users doc role='admin' or status='active' while suspended. | Regular user | Write denied by Firestore rules. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-LIST-001 | UC-06 | FR-002 | Listing Intake | Submit a complete valid listing | Functional | High | Signed in | 1. Complete Create Listing. 2. Upload >=4 photos + both documents. 3. Add showing window. 4. Submit. | Valid listing data | Listing saved as pending; not in public search; appears in admin queue. | Existing (QA doc) | Passed (Dev) |  |  |  | Intake rules extended in v1.1.
TC-INTAKE-001 | UC-06 | FR-002 | Listing Intake | Description length rules (updated) | Negative/Boundary | High | Otherwise valid listing | 1. Submit with empty/whitespace description. 2. Submit with 120 words. 3. Submit with 410 words. | Descriptions: blank, 120 words, 410 words | Blank -> blocked. 120 words -> ACCEPTED (150 is a recommendation hint only). 410 words -> blocked with inline guidance. | Updated | Not Run |  |  |  | Expected result changed by P1 description fix (was: 120 words blocked). Update QA doc Table 4 & FR-002.
TC-INTAKE-001B | UC-06 | FR-002 | Listing Intake | Description boundaries 1 / 400 / 401 words | Boundary | Medium | Otherwise valid listing | 1. Submit 1-word, 400-word, 401-word descriptions. | Generated text | 1 and 400 accepted; 401 blocked. | New | Not Run
TC-INTAKE-002 | UC-06 | FR-002 | Listing Intake | Fewer than 4 photos | Negative | High | Otherwise valid listing | 1. Upload 3 photos. 2. Submit. | 3 images | Blocked: minimum 4 photos. | Existing (QA doc) | Passed (Dev) |  |  |  | Unit test.
TC-INTAKE-003 | UC-06 | FR-003 | Listing Intake | Missing government ID or ownership document | Negative | High | Otherwise valid listing | 1. Upload only ownership doc; submit. 2. Upload only gov ID; submit. | One document each | Both blocked until both documents are uploaded. | Existing (QA doc) | Passed (Dev)
TC-INTAKE-004 | UC-06 | FR-002 | Listing Intake | Invalid or missing showing window | Negative | High | Otherwise valid listing | 1. Remove all windows. 2. Enter end time before start time. | Window 14:00–10:00 | Blocked: at least one valid window required. | Existing (QA doc) | Passed (Dev)
TC-INTAKE-005 | UC-07 | FR-003 | Listing Intake | Request changes then resubmit | Functional | High | Pending listing | 1. Admin selects Request changes with note. 2. Owner opens My Listings, sees note. 3. Edits and resubmits. | Pending listing | Owner sees changes-requested + note; resubmission returns listing to pending. | Existing (QA doc) | Passed (Dev)
TC-INTAKE-006 | UC-07 | FR-002 | Listing Intake | Edit parity with creation rules | Negative | High | Existing listing | 1. Edit listing; reduce to 2 photos / blank description. 2. Save. | Existing listing | Same validation errors as creation; not saved. | Existing (QA doc) | Passed (Dev)
TC-INTAKE-007 | UC-06 | FR-002 | Listing Intake | Each required field missing | Negative | High | Create Listing form | 1. For each of type, address/area, city, bedrooms, bathrooms, size, rent, availability date, amenities: leave blank and submit. | Otherwise valid listing | Field-level inline error under the missing field; no listing doc created. | New | Not Run |  |  |  | Data-driven: 9 iterations.
TC-INTAKE-008 | UC-06 | FR-002 | Listing Intake | Numeric field validation | Negative/Boundary | Medium | Create Listing form | 1. Enter 0 / negative / non-numeric for rent, size, bedrooms, bathrooms. | -1, 0, 'abc' | Rejected with inline error. | New | Not Run
TC-INTAKE-009 | UC-06 | FR-002 | Listing Intake | Non-image or oversized photo upload | Negative | Medium | Create Listing form | 1. Upload a .exe/.txt as photo. 2. Upload very large image. | Invalid files | Rejected with clear message; no broken URL saved. | New | Not Run
TC-INTAKE-010 | UC-06 | FR-003 | Listing Intake | Upload failure feedback | Negative | Medium | Create Listing form | 1. Go offline during photo/document upload. | DevTools offline | Error shown with retry; submit stays blocked until upload succeeds. | New | Not Run |  |  |  | Design Guide B8 feedback rule.
TC-INTAKE-011 | UC-06 | FR-002 | Listing Intake | Multi-step form progress indicator | UI | Low | Create Listing form | 1. Walk through details -> photos -> documents steps. | - | Progress indicator shown; data kept when moving back/forward. | New | Not Run |  |  |  | Design Guide B8.
TC-INTAKE-012 | UC-06 | FR-003 | Listing Intake | Limitation copy shown | UI | Medium | Create Listing / Listing Detail | 1. Read verification copy. | - | UI states review is a document-plausibility check, not a legal title search. | New | Not Run |  |  |  | Build Instructions §7.
TC-INTAKE-013 | UC-07 | FR-002 | Listing Intake | Non-owner cannot edit listing | Security | High | Listing owned by user A | 1. As user B open /listings/{id}/edit. 2. Attempt direct update. | Two users | UI denies; Firestore update denied. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-VER-001 | UC-10 | FR-003 | Admin Listing Review | Approve a pending listing | Functional | High | Admin; pending listing | 1. Open Listing Review Queue. 2. Approve. | Seeded pending listing | verified + verifiedAt; appears in search with 'Verified – document reviewed' badge; owner notified. | Existing (QA doc) | Passed (Dev) |  |  |  | Photo/PDF rendering fixed (BUG-002).
TC-VER-002 | UC-41 | FR-003 | Admin Listing Review | Signed-out read of pending listing | Security | High | Pending listing | 1. Sign out. 2. Read pending listing by ID. | Pending listing ID | Read denied. | Existing (QA doc) | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-VER-003 | UC-10 | FR-003 | Admin Listing Review | Reject a listing with note | Functional | High | Admin; pending listing | 1. Reject with reason. | Pending listing | Status rejected; owner sees reason and is notified; never public. | New | Not Run
TC-VER-004 | UC-10 | FR-003 | Admin Listing Review | Queue shows both documents + account name | Functional | High | Pending listing with photo + PDF docs | 1. Open item in queue. | JPG ID + PDF deed | Photos, ownership doc and gov ID viewable next to account name. | New | Not Run |  |  |  | Regression for BUG-002; depends on BUG-006.
TC-VER-005 | UC-10 | FR-003 | Admin Listing Review | Non-admin cannot approve | Security | High | Regular user | 1. Direct write verificationStatus='verified' on own listing. | Own pending listing | Write denied. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-VER-006 | UC-10 | FR-003 | Admin Listing Review | Documents not exposed publicly | Security | High | Verified listing | 1. As guest, open listing detail and inspect network/page source. | Verified listing | No ownership/ID document URLs in public data. | New | Blocked |  |  |  | Blocked by F-16: needs private documents + migration (v1.4). See TC-DOC-001 to 009.
TC-VER-007 | UC-10 | FR-003 | Admin Listing Review | Empty review queue state | UI | Low | No pending listings | 1. Open queue. | - | Empty-state message, no error. | New | Not Run
TC-SRCH-001 | UC-11 | FR-004 | Search & Browse | Filter by city, price, type | Functional | High | Seeded listings | 1. Open Browse. 2. Apply filters. | Several cities | Only verified matches shown; empty state when none. | Existing (QA doc) | Passed (Dev)
TC-SRCH-002 | UC-11 | FR-010 | Search & Browse | Default sort by trust score | Integration | High | Workflow run | 1. Run workflow. 2. Check computedAt. 3. Open Browse. | Seeded bookings/ratings | Listings ordered by score, differing from price/recency sort. | Existing (QA doc) | Passed (Dev)
TC-SRCH-003 | UC-11 | FR-004 | Search & Browse | Pending/rejected/suspended listings excluded | Functional | High | Mixed statuses seeded | 1. Browse without filters. | Mixed listings | Only verified, non-suspended listings shown. | New | Not Run
TC-SRCH-004 | UC-11 | FR-004 | Search & Browse | Price range boundaries | Boundary | Medium | Seeded listings | 1. Set min=max=exact price of one listing. 2. Set min > max. | Known prices | Inclusive match; invalid range handled with message. | New | Not Run
TC-SRCH-005 | UC-12 | FR-004 | Search & Browse | Listing detail content above the fold | UI | Medium | Verified listing | 1. Open listing at 390 px. | - | Verified badge + trust score visible without scrolling; Request Booking is the dominant CTA. | New | Not Run |  |  |  | Design Guide Part C.
TC-SRCH-006 | UC-12 | FR-001 | Search & Browse | Guest clicks Request Booking | Functional | Medium | Signed out | 1. Open listing. 2. Click Request Booking. | - | Prompted to sign in; returns to listing after login. | New | Not Run
TC-SRCH-007 | UC-12 | FR-004 | Search & Browse | Home shows live verified listings only | Functional | Low | - | 1. Open Home. | - | Rental showcase uses verified live listings; no sample cards. | New | Not Run |  |  |  | P2 navigation change.
TC-BOOK-001 | UC-14 | FR-005 | Booking | Request free dates | Functional | High | Renter signed in | 1. Open verified listing. 2. Request free dates. | No Confirmed booking on Jan 5–8 | Booking Pending; owner sees request. | Existing (QA doc) | Passed (Dev)
TC-BOOK-002 | UC-14 | FR-006 | Booking | Overlap with Confirmed booking rejected | Negative | High | Confirmed Dec 10–15 | 1. Request Dec 12–18. | Seeded Confirmed booking | 'Dates unavailable'; no document created. | Existing (QA doc) | Passed (Dev)
TC-BOOK-003 | UC-15 | FR-006 | Booking | First confirmation wins | Functional | High | Two Pending same dates | 1. Owner confirms first. 2. Owner confirms second. | Two renters | Second confirmation rejected by confirm-time check. | Existing (QA doc) | Passed (Dev) |  |  |  | Passed on emulator only. Deployed app still has F-05 until the trusted API ships; live re-test = TC-API-006.
TC-BOOK-004 | UC-41 | FR-005 | Booking | Forbidden status 'Cancelled' by direct write | Security | High | Pending booking | 1. Direct write status='Cancelled'. | Pending booking | Denied; only 4 statuses allowed. | Existing (QA doc) | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-BOOK-005 | UC-16 | FR-005 | Booking | Decline pending request | Functional | High | Pending booking | 1. Owner declines. | Pending booking | Request removed; no forbidden status written. | Existing (QA doc) | Passed (Dev)
TC-BOOK-006 | UC-17 | FR-007 | Booking | Log deposit reference | Functional | High | Confirmed booking | 1. Renter enters GCash ref. 2. Save. | GC-TEST-0001 | Stored and visible to both; unavailable on Pending. | Existing (QA doc) | Passed (Dev)
TC-BOOK-007 | UC-18 | FR-008 | Booking | Renter marks booking completed (updated) | Functional | High | Confirmed booking | 1. Renter clicks Mark completed. | Confirmed booking | Completed once; rating prompt appears; dispute eligibility preserved. | Updated | Not Run |  |  |  | Was 'renter or owner'; owner button removed (P1).
TC-BOOK-008 | UC-18 | FR-008 | Booking | Owner has no Mark completed action | Functional | High | Owner with Confirmed booking | 1. Open Booking Requests as owner. | Confirmed booking | No Mark completed button on owner side. | New | Not Run |  |  |  | P1 duplicate completion.
TC-BOOK-009 | UC-14 | FR-006 | Booking | Adjacent date ranges (boundary) | Boundary | High | Confirmed Dec 10–15 | 1. Request Dec 15–18. 2. Request Dec 5–10. | Seeded Confirmed | Allowed (start < end && end > start rule; touching edges do not overlap). | New | Not Run |  |  |  | Confirm team's intended inclusive/exclusive rule.
TC-BOOK-010 | UC-14 | FR-006 | Booking | Range fully containing a Confirmed booking | Negative | High | Confirmed Dec 10–15 | 1. Request Dec 1–31. | Seeded Confirmed | Rejected. | New | Not Run
TC-BOOK-011 | UC-14 | FR-006 | Booking | Pending requests do not block each other | Functional | Medium | Existing Pending Dec 10–15 | 1. Second renter requests Dec 10–15. | Two renters | Second request created as Pending. | New | Not Run |  |  |  | Build Plan §4.
TC-BOOK-012 | UC-14 | FR-005 | Booking | Invalid dates | Negative | High | Renter | 1. End before start. 2. Start in the past. 3. No dates. | - | Blocked; Request button disabled with reason when no dates. | New | Not Run
TC-BOOK-013 | UC-14 | FR-005 | Booking | Owner cannot book own listing | Negative | Medium | Owner signed in | 1. Request booking on own listing. | Own listing | Blocked (UI + rules). | New | Not Run |  |  |  | Confirm intended behavior.
TC-BOOK-014 | UC-14 | FR-005 | Booking | Booking a non-verified listing | Security | High | Pending listing ID | 1. Direct create booking on pending listing. | Pending listing | Denied. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-BOOK-015 | UC-17 | FR-007 | Booking | Deposit reference on Pending / empty / by owner | Negative | High | Pending & Confirmed bookings | 1. Try on Pending. 2. Save empty. 3. Owner writes depositReference directly. | - | All rejected. | New | Not Run
TC-BOOK-016 | UC-18 | FR-008 | Booking | Completing a Pending booking | Negative | Medium | Pending booking | 1. Direct write status='Completed'. | Pending booking | Denied. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-BOOK-017 | UC-14 | FR-005 | Booking | Request outside showing windows | Negative | Medium | Listing with Sat 9–12 window | 1. Request Monday 15:00. | Seeded windows | Blocked or warned per spec. | New | Not Run |  |  |  | Confirm expected behavior.
TC-BOOK-018 | UC-14 | FR-013 | Booking | Booking still succeeds if notification write fails | Reliability | Medium | Renter | 1. Force notification write failure. 2. Submit request. | Test build / rules | Booking created; failure logged, not shown as booking failure. | New | Not Run |  |  |  | Best-effort notifications.
TC-JOB-001 | UC-19 | FR-008 | Ratings & Completion | Expired Confirmed booking auto-completes | Integration | High | Expired Confirmed booking | 1. Run workflow. 2. Check booking. | Seeded | Status Completed. | Existing (QA doc) | Passed (Dev) |  |  |  | Re-run in release QA.
TC-JOB-002 | UC-19 | FR-008 | Ratings & Completion | Non-expired or non-Confirmed untouched | Integration | Medium | Mixed bookings | 1. Run job. | Future Confirmed, expired Pending, Disputed | None changed. | New | Not Run
TC-JOB-003 | UC-19 | FR-008 | Ratings & Completion | Job cadence acceptable | Integration | Low | Workflow schedule | 1. Check scrape.yml cron. | - | Cadence documented; weekly delay accepted or shortened. | New | Not Run |  |  |  | Recommendation: move the workflow from weekly to daily (Infrastructure §6.3).
TC-RATE-001 | UC-22 | FR-008 | Ratings & Completion | Rate a completed booking | Functional | Medium | Completed booking | 1. Submit 1–5 + comment. | Completed booking | Rating saved; shown on listing reviews. | Existing (QA doc) | Passed (Dev)
TC-RATE-002 | UC-22 | FR-008 | Ratings & Completion | Rating on Pending booking by direct write | Security | High | Pending booking | 1. Direct write rating. | Pending booking | Denied. | Existing (QA doc) | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-RATE-003 | UC-22 | FR-008 | Ratings & Completion | Score outside 1–5 | Negative | Medium | Completed booking | 1. Submit 0 or 6. | 0, 6 | Rejected. | New | Not Run
TC-RATE-004 | UC-22 | FR-008 | Ratings & Completion | Duplicate rating by same rater | Negative | Medium | Already rated | 1. Rate again. | - | Blocked. | New | Not Run |  |  |  | Max 2 ratings per booking.
TC-RATE-005 | UC-22 | FR-008 | Ratings & Completion | Non-participant rates booking | Security | Medium | Completed booking | 1. As unrelated user, direct write rating. | - | Denied. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-DISP-001 | UC-23 | FR-009 | Disputes | Raise a dispute (updated) | Functional | High | Confirmed booking | 1. Renter opens booking. 2. Raise Dispute with reason. | Seeded Confirmed | Dispute Open in admin queue; booking -> Disputed; prior status + dispute link stored; admins notified. | Updated | Not Run |  |  |  | Booking state now changes on submit (P1 dispute).
TC-DISP-002 | UC-24 | FR-009 | Disputes | Founded dispute | Functional | High | Open dispute | 1. Admin marks Founded with notes. | Open dispute | Owner account + listing suspended; booking stays Disputed; public flag shows; reporter notified. | Existing (QA doc) | Passed (Dev) |  |  |  | Re-run after P1 change.
TC-DISP-003 | UC-24 | FR-009 | Disputes | Dismissed dispute restores prior status (updated) | Functional | High | Open dispute on Confirmed booking | 1. Admin marks Dismissed. | Open dispute | No suspension/flag; booking restored to Confirmed; reporter notified. | Updated | Not Run |  |  |  | Restore behavior added in P1.
TC-DISP-004 | UC-23 | FR-009 | Disputes | Duplicate open dispute blocked | Negative | High | Open dispute exists | 1. Raise another dispute on same booking. | - | Blocked. | New | Not Run
TC-DISP-005 | UC-23 | FR-009 | Disputes | Dispute on Pending booking | Negative | Medium | Pending booking | 1. Try Raise Dispute. | - | Not allowed. | New | Not Run
TC-DISP-006 | UC-23 | FR-009 | Disputes | Empty dispute reason | Negative | Medium | Confirmed booking | 1. Submit blank reason. | - | Inline error. | New | Not Run
TC-DISP-007 | UC-24 | FR-009 | Disputes | Audit trail completeness | Functional | High | Resolved dispute | 1. Inspect dispute record. | - | Has bookingId, raisedBy, reason, decision, notes, resolver, createdAt, resolvedAt. | New | Not Run |  |  |  | P1 acceptance.
TC-DISP-008 | UC-24 | FR-009 | Disputes | Suspended owner's listings hidden | Integration | High | Founded dispute | 1. Browse as guest. | Suspended owner | Suspended listing no longer in search. | New | Not Run
TC-DISP-009 | UC-23 | FR-009 | Disputes | Dispute on Completed booking within window | Functional | Medium | Completed booking | 1. Raise dispute. | - | Allowed/blocked per agreed time window. | New | Not Run |  |  |  | Team policy decision needed: how long after Completed a dispute may be raised (proposed 7 days).
TC-PROF-001 | UC-13 | FR-018 | Public Profile | Flagged owner profile | Functional | Medium | Owner with 1 Founded | 1. Open public profile. | Seeded | Shows trust score, rating, '1 founded dispute' warning. | Existing (QA doc) | Passed (Dev)
TC-PROF-002 | UC-13 | FR-018 | Public Profile | Dismissed disputes don't flag | Functional | Medium | Owner with only Dismissed | 1. Open profile. | - | No warning shown. | New | Not Run
TC-TRUST-001 | UC-25 | FR-010 | Trust & Fairness Score | Score formula matches hand calculation | Unit | High | Seed data | 1. Run score functions. 2. Compare with manual calc. | Seed data | Sub-scores and total match. | Existing (QA doc) | Passed (Dev)
TC-TRUST-002 | UC-25 | FR-010 | Trust & Fairness Score | Only Completed bookings count | Unit | High | Seed listing | 1. Add Pending + Completed. 2. Recompute. | - | Only Completed affects booking score. | Existing (QA doc) | Passed (Dev)
TC-TRUST-003 | UC-25 | FR-010 | Trust & Fairness Score | Recency weighting | Unit | Medium | Completed bookings 2 and 8 months ago | 1. Compute booking score. | - | 1.0 + 0.5 = 1.5. | New | Not Run |  |  |  | Build Plan §5.
TC-TRUST-004 | UC-25 | FR-010 | Trust & Fairness Score | No ratings - no NaN | Unit | High | Listing without ratings | 1. Recompute. | - | Rating score 0/default; total is a valid number. | New | Not Run
TC-TRUST-005 | UC-12 | FR-010 | Trust & Fairness Score | Trust score display with cue | UI | Low | Verified listing | 1. Open listing detail. | - | Numeric score + plain-language cue shown. | New | Not Run |  |  |  | Design Guide B5.
TC-FAIR-001 | UC-25 | FR-010 | Trust & Fairness Score | Above/At/Below market labels | Unit/Integration | High | Comparables seeded | 1. Recompute for listings at +20%, 0%, -20% vs median. | Seeded | Above market / At market / Below market. | Existing (QA doc) | Not Run
TC-FAIR-002 | UC-25 | FR-010 | Trust & Fairness Score | Insufficient data | Unit | High | No comparables | 1. Recompute. | Isolated listing | 'Insufficient data'. | Existing (QA doc) | Not Run
TC-FAIR-003 | UC-26 | FR-011 | Trust & Fairness Score | Self-booking pattern flagged | Integration | High | 3 completed in 30 days, same pair | 1. Run workflow. | Synthetic | manualReviewRequired=true; selfBookingPatternCount=3. | Existing (QA doc) | Not Run
TC-FAIR-004 | UC-25 | FR-010 | Trust & Fairness Score | ±15% threshold boundaries | Boundary | Medium | Comparables | 1. Compute at +15%, +15.1%, -15%, -15.1%. | - | ±15% = At market; beyond = Above/Below. | New | Not Run
TC-FAIR-005 | UC-25 | FR-010 | Trust & Fairness Score | 20% size band filter | Unit | Medium | Comparables of varied size | 1. Include 25% larger listing. | - | Excluded from median. | New | Not Run
TC-FAIR-006 | UC-26 | FR-011 | Trust & Fairness Score | No flag below threshold | Unit | Medium | 2 bookings in 30 days, or 3 over 45 days | 1. Recompute. | - | manualReviewRequired=false. | New | Not Run
TC-DASH-001 | UC-27 | FR-012 | Owner Dashboard & My Listings | Dashboard counts match Firestore | Functional | Low | Seeded owner | 1. Open My Dashboard at 390 px. | Seeded | Counts match. | Existing (QA doc) | Not Run
TC-DASH-002 | UC-27 | FR-012 | Owner Dashboard & My Listings | New user dashboard | UI | Low | New account | 1. Open dashboard. | - | Zeros/empty state with CTA. | New | Not Run
TC-MYL-001 | UC-09 | FR-023 | Owner Dashboard & My Listings | Listing cards show key details | Functional | Medium | Owner with multiple listings | 1. Open My Listings. | Mixed statuses | Photo, city, type, bedrooms, price, status, review note, View/Edit on each card. | New | Not Run
TC-MYL-002 | UC-09 | FR-023 | Owner Dashboard & My Listings | Per-listing pending counts | Functional | Medium | Listings with 0 and 2 pending | 1. Open My Listings. | - | Correct counts per listing. | New | Not Run
TC-MYL-003 | UC-09 | FR-023 | Owner Dashboard & My Listings | Count load failure is not zero | Negative | Medium | Owner | 1. Block bookings query. 2. Open My Listings. | DevTools | 'Unavailable' state, not 0. | New | Not Run
TC-MYL-004 | UC-09 | FR-023 | Owner Dashboard & My Listings | Request link filters by listing | Functional | Medium | Listing with requests | 1. Tap request count. 2. Tap 'all requests'. | - | Booking Requests tab filtered; back link shows all. | New | Not Run
TC-MYL-005 | UC-09 | FR-023 | Owner Dashboard & My Listings | Private data excluded | Security | High | Owner | 1. Inspect My Listings. | - | No exact address or document URLs on cards. | New | Not Run
TC-MYL-006 | UC-09 | FR-023 | Owner Dashboard & My Listings | Narrow viewport layout | UI | Low | Owner | 1. View at 360/390 px. | - | Cards readable, no overflow. | New | Not Run
TC-NOTIF-001 | UC-28 | FR-013 | Notifications | Owner notified of booking request | Functional | High | Renter + owner | 1. Renter requests. 2. Owner opens bell. 3. Mark read. | - | Unread notification; count clears. | Existing (QA doc) | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-NOTIF-002 | UC-28 | FR-013 | Notifications | Renter notified of confirmation | Functional | High | Renter + owner | 1. Owner confirms. 2. Renter checks bell. | - | Confirmation notification received. | Existing (QA doc) | Blocked |  |  |  | Needs booking confirmation on live app: blocked by F-05 until the trusted API is deployed (v1.4). See TC-API-004.
TC-NOTIF-003 | UC-29 | FR-013 | Notifications | Dispute notifications | Functional | High | Renter + admin | 1. Raise dispute. 2. Admin resolves. | - | Admins notified on submission; reporter on resolution; owner notified of listing decisions. | Existing (QA doc) | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-NOTIF-004 | UC-41 | FR-013 | Notifications | Cross-user notification access | Security | High | Two users | 1. As A read/create B's notifications. | - | Denied. | Existing (QA doc) | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-NOTIF-005 | UC-29 | FR-020 | Notifications | Admin feed contains disputes only | Functional | High | Admin who also owns listings | 1. Create booking request on admin's listing and a dispute. 2. Open admin bell. | - | Admin bell/inbox under /admin shows dispute only; booking request appears in admin's personal user feed. | New | Not Run |  |  |  | P0 notification split.
TC-NOTIF-006 | UC-29 | FR-020 | Notifications | No booking-request broadcast to __admins__ | Security | High | Regular user | 1. Direct create notification to __admins__ with type booking-request. | - | Denied. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-NOTIF-007 | UC-29 | FR-020 | Notifications | Regular user cannot read admin feed | Security | High | Regular user | 1. Query __admins__ notifications. | - | Denied. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-NOTIF-008 | UC-29 | FR-020 | Notifications | Legacy admin booking notices hidden | Functional | Medium | Old booking-request docs in __admins__ | 1. Open admin inbox. | Legacy data | Filtered out; not readable after rules deploy. | New | Not Run
TC-NOTIF-009 | UC-29 | FR-020 | Notifications | Admins cannot create broadcasts | Security | Medium | Admin | 1. Direct create notification to __admins__. | - | Denied. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-NOTIF-010 | UC-28 | FR-013 | Notifications | Mark all read / empty inbox | Functional | Low | User | 1. Mark all read. 2. New user opens inbox. | - | Count 0; empty state shown. | New | Not Run
TC-NOTIF-011 | UC-28 | FR-013 | Notifications | Listing decision notification | Functional | Medium | Owner | 1. Admin approves/requests changes/rejects. | - | Owner notified for each decision. | New | Not Run
TC-MAP-001 | UC-08 | FR-022 | Listing Map & Privacy | Search address and place pin | Functional | Medium | Create/Edit listing | 1. Type 'Santa Rosa, Laguna'. 2. Select result. | PH address | Pin placed; attribution shown. | New | Not Run
TC-MAP-002 | UC-08 | FR-022 | Listing Map & Privacy | PH-specific geocoder retry | Functional | Low | - | 1. Enter full street address without 'Philippines'. | Full address | Resolves via PH retry. | New | Not Run
TC-MAP-003 | UC-08 | FR-022 | Listing Map & Privacy | 'Use my exact address' shortcut renders | Functional / Regression | High | Private address prefilled | 1. Open edit listing with address. 2. Hard reload (clear cache). 3. Check map search box. | Listing with address | Button visible; clicking geocodes private address and places pin. | New | Passed | Shortcut visible after a private address was entered (Sep 30 live test). | Team (Sep 30 run) | 2026-09-30 | Resolved: earlier browser-visibility bug closed by the Sep 30 live run.
TC-MAP-004 | UC-08 | FR-022 | Listing Map & Privacy | Public doc stores only 5-char geohash | Security | High | Listing with pin | 1. Inspect public listing doc. | - | Only geohash (5 chars) + approximate flag; no lat/long, no address. | New | Not Run
TC-MAP-005 | UC-08 | FR-022 | Listing Map & Privacy | Invalid pin rejected | Negative | Medium | - | 1. Direct write lat/long or 7-char geohash to listing. | - | Denied by rules. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-MAP-006 | UC-12 | FR-022 | Listing Map & Privacy | Legacy listing without pin | Regression | Medium | Old listing | 1. Open detail. | - | Map section hidden; page works. | New | Not Run
TC-MAP-007 | UC-41 | FR-022 | Listing Map & Privacy | listingPrivate access | Security | High | Listing | 1. As guest/other user read listingPrivate/{id}. 2. As owner/admin read. | - | Others denied; owner/admin allowed. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-MAP-008 | UC-06 | FR-022 | Listing Map & Privacy | New listing cannot contain public address | Security | High | - | 1. Direct create listing with address field. | - | Denied. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-MAP-009 | UC-20 | FR-024 | Listing Map & Privacy | Exact address after confirmation | Functional | High | Confirmed booking | 1. Renter opens confirmed booking. | - | Exact address shown. | New | Not Run |  |  |  | Reported working in Sep 30 live test. Re-run after v1.4 because confirmation now goes through the API.
TC-MAP-010 | UC-20 | FR-024 | Listing Map & Privacy | Exact address hidden before confirmation | Security | High | Pending booking / unrelated user | 1. Open booking / query address. | - | Address not shown/denied. | New | Not Run
TC-MAP-011 | UC-40 | FR-022 | Listing Map & Privacy | Migration dry run | Functional | High | Backup taken | 1. Run migrate_listing_addresses.py. | Live project | Counts reported; no writes. | New | Not Run
TC-MAP-012 | UC-40 | FR-022 | Listing Map & Privacy | Migration apply is idempotent | Functional | High | Dry run reviewed | 1. Run --apply twice. | - | Second run changes nothing; existing private addresses kept; conflicts reported. | New | Not Run
TC-NAV-001 | UC-21 | FR-021 | Navigation & Settings | Account menu has no duplicates | UI | Medium | Signed in | 1. Open account menu. | - | Single My Activity entry; no Saved Searches. | New | Not Run
TC-NAV-002 | UC-21 | FR-021 | Navigation & Settings | My Activity tabs + URL | Functional | Medium | Signed in | 1. Switch each tab. 2. Reload. 3. Copy URL to new tab. | - | Tab state in URL and restored. | New | Not Run
TC-NAV-003 | UC-21 | FR-021 | Navigation & Settings | Old direct routes still work | Regression | Low | - | 1. Open previous My Bookings / Requests routes. | - | Pages load. | New | Not Run
TC-NAV-004 | UC-38 | FR-017 | Navigation & Settings | /saved-searches redirects | Regression | Low | Existing savedSearches docs | 1. Open /saved-searches. | - | Redirect to Browse; records remain in Firestore. | New | Not Run
TC-SET-001 | UC-37 | FR-021 | Navigation & Settings | System/Light/Dark appearance | Functional | Medium | - | 1. Select each mode. 2. Change OS theme in System mode. | - | Theme applied; System follows OS. | New | Not Run
TC-SET-002 | UC-37 | FR-021 | Navigation & Settings | Accessibility toggles persist | Functional | Medium | - | 1. Enable Larger text, High contrast, Reduce motion. 2. Reload. | - | Preferences persist and apply. | New | Not Run
TC-SET-003 | UC-37 | FR-021 | Navigation & Settings | Switch visibility in dark mode | UI | Low | Dark mode | 1. Open Settings. | - | Switch thumbs clearly visible; contrast >= 3:1. | New | Not Run
TC-SAVE-001 | UC-38 | FR-017 | Saved Searches (Retired) | Save filters | Functional | Low | - | Retired | - | Retired with Saved Searches removal. | Retired | Retired |  |  |  | Replaced by TC-NAV-004.
TC-SAVE-002 | UC-38 | FR-017 | Saved Searches (Retired) | Alert on new match | Functional | Low | - | Retired | - | Retired; never implemented. | Retired | Retired |  |  |  | Remove FR-017 from active scope.
TC-BANK-001 | UC-30 | FR-014 | Bank Catalog & Loan | Scraper upserts with lastSeen | Integration | Medium | Live Metrobank | 1. Run scraper. 2. Open catalog. | - | metrobank_<ref> docs with lastSeen; 'Last verified' shown. | Existing (QA doc) | Passed (Dev)
TC-BANK-002 | UC-30 | FR-014 | Bank Catalog & Loan | Missing records delisted | Integration | Medium | Existing active record | 1. Run when record absent. | - | status delisted; lastSeen updated. | Existing (QA doc) | Passed (Dev)
TC-BANK-003 | UC-41 | FR-014 | Bank Catalog & Loan | Client write to bankProperties | Security | Medium | Normal user | 1. Direct write. | - | Denied. | Existing (QA doc) | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-BANK-004 | UC-30 | FR-014 | Bank Catalog & Loan | No duplicates on re-run | Integration | Medium | - | 1. Run scraper twice. | - | Same doc count; deterministic IDs. | New | Not Run
TC-BANK-005 | UC-31 | FR-014 | Bank Catalog & Loan | Catalog filters | Functional | Medium | Populated catalog | 1. Filter bank/city/price. | - | Correct results; empty state. | New | Not Run
TC-BANK-006 | UC-31 | FR-014 | Bank Catalog & Loan | Image fallback | UI | Low | Property without image | 1. Open catalog. | - | Fallback image, no broken icon. | New | Not Run |  |  |  | TODO cleanup 2026-09-30.
TC-BANK-007 | UC-33 | FR-016 | Bank Catalog & Loan | Admin scrape log view | UI | Low | Admin | 1. Open Bank Catalog Status. | - | Last run shown; intended inset/padding. | New | Not Run
TC-LOAN-001 | UC-32 | FR-015 | Bank Catalog & Loan | Known amortization value | Unit | Medium | - | 1. 2,000,000; 20% down; 6%; 20 yrs. | - | ≈ PHP 11,462.90. | Existing (QA doc) | Passed (Dev)
TC-LOAN-002 | UC-32 | FR-015 | Bank Catalog & Loan | Invalid inputs | Negative | Medium | - | 1. 0% rate, negative price, empty term. | - | Validation; no NaN/Infinity. | Existing (QA doc) | Not Run
TC-LOAN-003 | UC-32 | FR-015 | Bank Catalog & Loan | Price pre-filled from property | Functional | Low | Bank property | 1. Open detail. | - | Price pre-filled. | New | Not Run
TC-LOAN-004 | UC-32 | FR-015 | Bank Catalog & Loan | 0% interest computes P/n | Unit | Medium | - | 1. 1,200,000, 0% down, 0%, 10 yrs. | - | PHP 10,000.00. | New | Not Run
TC-ADM-001 | UC-36 | FR-016 | Admin Access & Management | Suspend and reinstate | Functional | Medium | Admin | 1. Suspend user. 2. Reinstate. | Test user | Status toggles; suspended user blocked. | Existing (QA doc) | Passed (Dev)
TC-ADM-002 | UC-35 | FR-016 | Admin Access & Management | Dashboard counts | Functional | Medium | Admin | 1. Open Admin Dashboard. | Seeded | Pending listings + open disputes match Firestore. | New | Not Run
TC-ADM-003 | UC-34 | FR-019 | Admin Access & Management | Active admin accesses /admin | Functional | High | Active admin | 1. Open /admin and nested routes directly. | - | Loading status then admin UI renders. | New | Not Run |  |  |  | P0.
TC-ADM-004 | UC-34 | FR-019 | Admin Access & Management | Regular user blocked | Security | High | Regular user | 1. Open /admin/listings directly. | - | Redirected; no admin content flash. | New | Not Run
TC-ADM-005 | UC-34 | FR-019 | Admin Access & Management | Suspended admin blocked | Security | High | Admin with status suspended | 1. Open /admin. | - | Suspended screen. | New | Not Run
TC-ADM-006 | UC-34 | FR-019 | Admin Access & Management | Missing/unreadable profile fails closed | Security | High | Auth user without profile | 1. Open /admin. | - | Retryable verification message; no admin UI. | New | Not Run
TC-ADM-007 | UC-34 | FR-019 | Admin Access & Management | Non-admin Firestore admin reads | Security | High | Regular user | 1. Query pending listings / disputes directly. | - | Denied. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-ADM-008 | UC-34 | FR-019 | Admin Access & Management | Admin guard unit tests | Unit | High | - | 1. Run node --test. | - | 5 access-state policy tests pass. | New | Passed |  |  |  | Included in the 47 passing Node tests (Oct 1).
TC-ADM-009 | UC-36 | FR-016 | Admin Access & Management | Suspend requires confirmation | UI | Low | Admin | 1. Click Suspend. | - | Danger-styled button + confirm step. | New | Not Run |  |  |  | Design Guide B5.
TC-SEC-001 | UC-41 | FR-005 | Security (Firestore Rules) | Renter confirms another's booking | Security | High | Seeded booking | 1. Direct write status Confirmed. | - | Denied. | Existing (QA doc) | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-SEC-002 | UC-41 | FR-006 | Security (Firestore Rules) | Owner confirms overlapping booking | Security | High | Seeded overlap | 1. As owner, attempt a direct Firestore update of status to Confirmed. 2. Call the API to confirm an overlapping request. | - | Direct write denied by rules; API returns 409 and booking stays Pending. | Existing (QA doc) | Blocked |  |  |  | Blocked by F-05: confirmation must go through the trusted API. Re-run as TC-API-005/006 plus a direct-write denial check.
TC-SEC-003 | UC-41 | FR-009 | Security (Firestore Rules) | Non-admin resolves dispute; non-owner reads docs | Security | High | Seeded | 1. Resolve as non-admin. 2. Read private fields. | - | Both denied. | Existing (QA doc) | Blocked |  |  |  | Dispute part: run now. Document part blocked by F-16 (v1.4).
TC-SEC-004 | UC-30 | NFR-SEC | Security (Firestore Rules) | Secret not printed in logs | Security | High | GitHub Actions | 1. Run workflow. 2. Inspect logs. | - | Secret masked; data + trustScores updated. | Existing (QA doc) | Not Run
TC-SEC-005 | UC-41 | NFR-SEC | Security (Firestore Rules) | Unmatched collection deny-all | Security | Medium | - | 1. Write to random collection. | - | Denied. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-SEC-006 | UC-41 | FR-010 | Security (Firestore Rules) | Client write to trustScores | Security | High | User | 1. Direct write own listing score. | - | Denied. | New | Not Run |  |  |  | Unblocked 2026-10-01: rules deployed to trusthome-ph (commit a1fe48e). Run on the live test project.
TC-SEC-007 | UC-41 | NFR-SEC | Security (Firestore Rules) | Rules compile and deploy | Deployment | Critical | Firebase CLI | 1. firebase deploy --only firestore:rules. | - | Deploys without errors. | New | Passed | Rules deployed to trusthome-ph without errors (commit a1fe48e). |  | 2026-10-01 | Deployed. Unblocked the rules-only cases.
TC-HARD-001 | UC-42 | NFR-REL | Release & Non-functional | Lazy route fallback | Functional | Medium | Throttled | 1. Navigate on slow 3G. | - | Accessible loading fallback. | Existing (QA doc) | Not Run
TC-HARD-002 | UC-42 | NFR-REL | Release & Non-functional | Error boundary | Functional | Medium | Test build | 1. Trigger runtime error. | - | Error screen with Reload. | Existing (QA doc) | Not Run
TC-HARD-003 | UC-35 | FR-016 | Release & Non-functional | Admin retry after load error | Functional | Medium | Admin | 1. Block Firestore. 2. Open dashboard. 3. Retry. | - | Error + Retry; loads after. | Existing (QA doc) | Not Run |  |  |  | BUG-001 regression.
TC-AUTO-001 | - | All | Release & Non-functional | node --test | Unit | High | dev | Run node --test. | - | All pass. | Updated | Passed |  |  |  | Now 47/47 (Oct 1; was 33).
TC-AUTO-002 | - | All | Release & Non-functional | npm run lint | Static | High | dev | Run lint. | - | No errors. | Existing (QA doc) | Passed
TC-AUTO-003 | - | All | Release & Non-functional | npm run build | Build | High | dev | Run build. | - | Succeeds; no large-bundle warning. | Updated | Passed |  |  |  | Vendor chunk split resolved BUG-007.
TC-AUTO-004 | - | All | Release & Non-functional | Python unittest | Unit | High | bank_scraper | Run unittest discover. | - | All pass. | Updated | Passed |  |  |  | Now 23/23 (Oct 1; was 14).
TC-AUTO-005 | UC-39 | NFR | Release & Non-functional | Seed demo data | Integration | Medium | Live project | Dry run then seed. | - | Synthetic data created; no real IDs/Auth users. | Existing (QA doc) | Passed |  |  |  | Re-run in smoke test.
TC-UI-001 | - | NFR-USE | Release & Non-functional | Cross-browser & viewport walkthrough | UAT | High | Deployed build | User pages at 390 px, admin at 1280 px in Chrome, Edge, Firefox, mobile. | - | Layouts intact; 44 px targets; focus visible; labeled statuses. | Existing (QA doc) | Not Run
TC-UI-002 | - | NFR-USE | Release & Non-functional | Accessibility checks | UAT | Medium | Deployed build | 1. Keyboard-only navigation. 2. Contrast audit (Lighthouse/axe). 3. Photo alt text. | - | WCAG AA contrast; status never color-only; alt text present. | New | Not Run |  |  |  | Design Guide B7.
TC-UI-003 | - | NFR-USE | Release & Non-functional | Button states and padding | UI | Low | - | 1. Hover/press/disable buttons. | - | States visible; consistent horizontal padding. | New | Not Run |  |  |  | Cleanup 2026-09-30.
TC-E2E-001 | - | All | Release & Non-functional | End-to-end renter–owner–admin smoke test | E2E | Critical | Deployed build + rules | 1. Owner lists. 2. Admin approves. 3. Renter books. 4. Owner confirms. 5. Renter logs deposit, views address. 6. Renter completes + rates. 7. Workflow recomputes. 8. Second booking disputed + resolved. | Test accounts | Every step succeeds; correct notifications; statuses consistent. | New | Not Run |  |  |  | Run after v1.4 deploy (API + private documents). Use the test-account matrix in QA & Testing Strategy §5.
TC-PURP-001 | UC-43 | FR-025 | Listing Purpose | Short-term rental listing | Functional | High | Signed in | 1. Create listing. 2. Choose For rent -> Short-term. 3. Enter nightly price. 4. Submit. | Nightly price 2,500 | Listing saved with purpose rent + nightly period; Browse/Detail show "per night". | New | Not Run
TC-PURP-002 | UC-43 | FR-025 | Listing Purpose | Long-term rental listing | Functional | High | Signed in | 1. Choose For rent -> Long-term. 2. Enter monthly rent. 3. Submit. | Monthly rent 18,000 | Saved with monthly period; shown as "/month". | New | Not Run
TC-PURP-003 | UC-43 | FR-025 | Listing Purpose | Sale listing cannot be booked | Negative | High | Verified sale listing | 1. Open sale listing as renter. 2. Try to request booking (UI and direct write). | Sale listing | No booking control shown; direct booking create denied by rules. | New | Not Run
TC-PURP-004 | UC-43 | FR-025 | Listing Purpose | Purpose required | Negative | Medium | Signed in | 1. Leave purpose unselected. 2. Submit. | - | Inline error; submission blocked. | New | Not Run
TC-PURP-005 | UC-43 | FR-025 | Listing Purpose | Purpose visible everywhere | UI | Medium | Listings of each purpose | 1. Check Browse, Detail, Admin review, My Listings. | 3 listings | Purpose chip and correct price label on all four pages. | New | Not Run
TC-PURP-006 | UC-25 | FR-025 | Listing Purpose | Fairness comparison excludes sale and mismatched periods | Functional | High | Mixed seed data | 1. Run trust recompute. 2. Inspect comparables for a monthly rental. | Seed set with sale + nightly + monthly | Only rentals with the same price period are comparables. | New | Not Run
TC-NOTIF-012 | UC-44 | FR-026 | Notifications | Admin alert on listing submission | Functional | High | Admin + owner accounts | 1. Owner submits listing. 2. Admin opens bell. | New listing | One listing_submitted alert linking to the review item. | New | Not Run
TC-NOTIF-013 | UC-44 | FR-026 | Notifications | Listing and alert written atomically | Negative | Medium | Emulator | 1. Force notification write to fail (rules). 2. Submit listing. | - | Neither listing nor alert is created; owner sees an error. | New | Not Run
TC-NOTIF-014 | UC-28 | FR-029 | Notifications | Open notification navigates and marks read | Functional | Medium | Unread notification | 1. Click notification row. | - | Navigates to stored link; row marked read; badge decrements. | New | Not Run
TC-NOTIF-015 | UC-28 | FR-029 | Notifications | Clear one and Clear read | Functional | Low | Mixed read/unread | 1. Clear one. 2. Clear read. | - | Selected row removed; all read rows removed; unread kept. | New | Not Run
TC-API-001 | UC-15 | FR-027 | Trusted API | Health endpoint | Deployment | High | API deployed | 1. GET /api/health. | - | 200 with version and region; no secrets in body. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-API-002 | UC-15 | FR-027 | Trusted API | Missing or invalid ID token | Security | Critical | API deployed | 1. Call confirm with no token. 2. With an expired/garbage token. | - | 401 with JSON error code; booking unchanged. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-API-003 | UC-15 | FR-027 | Trusted API | Non-owner cannot confirm | Security | Critical | Pending booking | 1. Renter or third user calls confirm. | Other account | 403; booking stays Pending. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-API-004 | UC-15 | FR-027 | Trusted API | Owner confirms free dates | Functional | Critical | Pending booking, no overlap | 1. Owner clicks Confirm. | Seed booking | 200; status Confirmed; renter notified; exact-address handoff readable by renter. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-API-005 | UC-15 | FR-006 | Trusted API | Overlap rejected at confirm time | Functional | Critical | Confirmed booking exists | 1. Owner confirms overlapping Pending request. | Overlapping dates | 409 BOOKING_OVERLAP; request stays Pending; clear message in UI. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-API-006 | UC-15 | FR-006 | Trusted API | Concurrent confirmations (F-05 close-out) | Concurrency | Critical | Two Pending, same dates | 1. Fire both confirm calls in parallel (script, 10 runs). | Two renters | Exactly one Confirmed in every run; other gets 409. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-API-007 | UC-15 | FR-027 | Trusted API | CORS blocks unknown origins | Security | High | API deployed | 1. Call from a non-allowlisted origin. | https://example.com | Browser blocks; no CORS allow header returned. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-API-008 | UC-15 | FR-027 | Trusted API | Suspended owner cannot confirm | Security | High | Suspended owner | 1. Call confirm. | - | 403 ACCOUNT_SUSPENDED. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-API-009 | UC-15 | FR-027 | Trusted API | API down shows service-unavailable | Negative | Medium | Point client at wrong API URL | 1. Click Confirm. | - | Clear service-unavailable message; no direct Firestore write attempted. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-API-010 | UC-15 | FR-027 | Trusted API | Repeat confirm is idempotent | Functional | Medium | Already Confirmed | 1. Call confirm twice. | - | Second call returns 200 already-confirmed (or 409 ALREADY_DECIDED); no duplicate notification. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-DOC-001 | UC-45 | FR-028 | Private Documents | New documents uploaded as authenticated assets | Security | Critical | v1.4 deployed | 1. Create listing with documents. 2. Open the bare Cloudinary URL without signature. | PDF + JPG | Bare URL returns 401/404; listingPrivate stores publicId, not a URL. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-DOC-002 | UC-45 | FR-028 | Private Documents | Admin preview via short-lived URL | Functional | Critical | Admin; listing with documents | 1. Open review item. | - | Both documents preview (image + PDF). | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-DOC-003 | UC-45 | FR-028 | Private Documents | Owner sees own documents | Functional | High | Owner | 1. Open own listing documents. | - | Preview loads. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-DOC-004 | UC-45 | FR-028 | Private Documents | Other user denied | Security | Critical | Third account | 1. Call document endpoint for someone else's listing. | - | 403; no URL returned. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-DOC-005 | UC-45 | FR-028 | Private Documents | Signed URL expires | Security | High | URL obtained | 1. Wait past TTL. 2. Open URL again. | TTL 5 min | Request rejected after expiry. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-DOC-006 | UC-06 | FR-028 | Private Documents | Photo preset rejects documents and oversize files | Negative | Medium | Unsigned photo preset | 1. Upload a PDF and a 15 MB image through the photo preset. | - | Cloudinary rejects; UI shows the reason. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-DOC-007 | UC-48 | FR-028 | Private Documents | Migration dry run | Operations | High | Backup taken | 1. Run migrate_verification_documents.py (dry run). | Live project | Counts listed; no writes. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-DOC-008 | UC-48 | FR-028 | Private Documents | Migration apply | Operations | Critical | Dry run reviewed | 1. Run with --apply. 2. Re-open 3 legacy URLs. | Live project | Legacy URLs stop loading; publicIds in listingPrivate; URL fields removed from listings. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-DOC-009 | UC-12 | FR-028 | Private Documents | Public listing data has no document references | Security | Critical | Migration applied | 1. As guest, inspect listing documents in network tab. | Any verified listing | No document URL or publicId in public data. | New | Not Run |  |  |  | Feature ships in v1.4 (trusted API). Run after the v1.4 deploy; record as Blocked if the API is not live by then.
TC-OPS-001 | UC-46 | NFR-SEC-02 | Operations | Old service-account key revoked | Security | Critical | Rotation done | 1. Try the old key with a small firebase-admin script. | Old key file | Authentication fails (invalid_grant). | New | Not Run
TC-OPS-002 | UC-46 | NFR-SEC-02 | Operations | Git history scan for secrets | Security | High | Repo cloned | 1. Run gitleaks (or git log search) on all branches. | - | No live credentials found; result recorded. | New | Not Run
TC-OPS-003 | UC-47 | NFR-REL-02 | Operations | Firestore JSON backup | Operations | High | Admin credentials | 1. Run backup script. 2. Compare counts. | - | Archive created; counts match console. | New | Not Run
TC-OPS-004 | UC-19 | NFR-REL | Operations | Scheduled workflow runs daily | Operations | Medium | Workflow updated | 1. Check Actions history for 2 consecutive days. | - | Scraper, completion job and trust recompute succeed; secret not printed. | New | Not Run
TC-OPS-005 | - | NFR-COST-01 | Operations | No paid service required | Operations | High | Release candidate | 1. Check Firebase plan, Cloudinary plan, Vercel plan. | - | Spark, Free, Hobby; no card on file anywhere. | New | Not Run
TC-OPS-006 | UC-39 | NFR | Operations | Demo data labelled correctly | Data | Medium | Live project | 1. Check the "Makati listing awaiting review" record shown as Verified. | - | Confirmed synthetic fixture and relabelled, or removed after confirmation. | New | Not Run
TC-AUTO-006 | - | NFR-SEC | Release & Non-functional | npm audit | Unit | Medium | dev | Run npm audit. | - | 0 high/critical vulnerabilities. | New | Passed | 0 vulnerabilities after pinning @grpc/grpc-js 1.13.6 |  | 2026-10-01

## Summary
Test Cases by Module and Status
Module | Total | Passed | Passed (Dev) | Failed | Blocked | Not Run | Retired | Executed | Pass Rate
Authentication
Listing Intake
Listing Purpose
Admin Listing Review
Private Documents
Search & Browse
Booking
Trusted API
Ratings & Completion
Disputes
Public Profile
Trust & Fairness Score
Owner Dashboard & My Listings
Notifications
Listing Map & Privacy
Navigation & Settings
Saved Searches (Retired)
Bank Catalog & Loan
Admin Access & Management
Security (Firestore Rules)
Operations
Release & Non-functional
TOTAL
By Origin
Existing (QA doc)
Updated
New
Retired
Use cases
Unassigned module check (should be 0)
Pass Rate = (Passed + Passed (Dev)) / Executed; Executed = Passed + Passed (Dev) + Failed.

## Proposed FRs
FR ID | Requirement | Priority | Source | Acceptance / Linked Tests
FR-002 (revise) | The system shall require a non-empty description of at most 400 words; 150 words is shown as a recommendation. | HIGH | Progress Report P1 Description | Empty/whitespace rejected; <150 words accepted; >400 rejected.
FR-008 (revise) | Only the renter manually marks a booking Completed; the scheduled job completes expired Confirmed bookings. | MEDIUM | Progress Report P1 Completion | Owner has no completion button; one Completed transition.
FR-009 (revise) | Submitting a dispute sets the booking to Disputed and records its prior status; Dismissed restores it; Founded keeps Disputed. | HIGH | Progress Report P1 Dispute | Booking and dispute states stay consistent; duplicate open disputes blocked.
FR-017 (retire) | Saved Searches removed; /saved-searches redirects to Browse without deleting records. | LOW | Cleanup 2026-09-30 | Redirect works; data preserved.
FR-019 | Only profiles with role admin and status active can render admin routes; missing/unreadable profiles fail closed with retry. | HIGH | Progress Report P0 Admin login | TC-ADM-003 to 008.
FR-020 | Admin notifications are limited to disputes; booking requests notify only the listing owner; feeds are isolated by rules. | HIGH | Progress Report P0 Notifications | TC-NOTIF-005 to 009.
FR-021 | One My Activity page (Listings, Bookings, Requests tabs) and Settings with System/Light/Dark plus persisted accessibility preferences. | LOW | Progress Report P2 Navigation | TC-NAV-001 to 004, TC-SET-001 to 003.
FR-022 | Optional approximate map pin stored as a 5-char geohash; exact address kept in listingPrivate readable by owner/admin only. | MEDIUM | Progress Report P2 Map | TC-MAP-001 to 008, 011, 012.
FR-023 | My Listings shows photo, city, type, bedrooms, price, status, review note and per-listing pending-request counts. | MEDIUM | Progress Report P1 Owner visibility | TC-MYL-001 to 006.
FR-024 | The renter sees the exact property address only after the booking is Confirmed. | HIGH | Build Instructions §2.1; cleanup 2026-09-30 | TC-MAP-009, 010.
FR-025 | Every listing shall declare a purpose (For rent: short-term nightly or long-term monthly; For sale: one-time asking price). Sale listings cannot be booked. | HIGH | Progress Report Oct 1 | TC-PURP-001 to 006.
FR-026 | Submitting a listing shall create an admin listing_submitted alert in the same write batch, linking to the review item. | MEDIUM | Progress Report Oct 1 | TC-NOTIF-012, 013.
FR-027 | Booking confirmation shall run only on the trusted API (Firebase ID token, owner + active check, Firestore transaction with per-listing lock). Clients cannot write status Confirmed. | CRITICAL | Architecture ADR-002; F-05 | TC-API-001 to 010, TC-SEC-002.
FR-028 | Verification documents shall be stored as Cloudinary authenticated assets and delivered only through short-lived signed URLs issued to the owner or an admin. | CRITICAL | Security & Privacy §5; F-16 | TC-DOC-001 to 009, TC-VER-006.
FR-029 | Notification rows navigate to their link, mark read on open, and support Clear and Clear read. | LOW | Progress Report Oct 1 | TC-NOTIF-014, 015.
NFR-COST-01 | The system shall run without any service that requires a credit card (Firebase Spark, Cloudinary Free, Vercel Hobby, GitHub Actions). | HIGH | Team constraint | TC-OPS-005.
NFR-SEC-02 | Service-account keys are issued per consumer, stored only as CI/host secrets, and rotated after any exposure. | HIGH | F-01 | TC-OPS-001, 002.
NFR-REL-02 | A restorable Firestore backup is taken before every migration or rules change. | HIGH | Infrastructure §8 | TC-OPS-003.